## Cost Rpt Summary
Sabey Construction & Development
Project Cost Summary - Current Projects
Date: | 2025-10-15
Job Number |  | Project Name | Project Lead | Hard Cost Budget | Soft Cost Budget | Total Budget | Committed Costs | Actual Costs Invoiced | Cost To Complete | Forecasted Cost @ Completion | Variance (Over)/Under | Estimated Completion Date | Notes
SDC Ashburn
22-8-502 | 22-3-302 | SDC-ASH Building A 54MW Design LLO | Max Wright | 0 | 5015010 | 5015010 | 4876694.19 | 4673491.84 | 0 | 4876694.19 | 138315.81 | 2025-11-30
22-8-503 | 22-3-303 | SDC-ASH-B AB1-1 & AB1-2 6MW Data Halls LLO | Max Wright | 44728039 | 685900 | 45413939 | 42753459.68 | 42738674.68 | 378266.34 | 43131726.02 | 2282212.98 | 2024-02-28 | Complete pending some Electrical issues.
24-8-013-ashasi | 24-3-013-ashasi | SDC-ASH-A Site LLO | Ted Satterthwaite | 20239283 | 761123 | 21000406 | 21250722.65 | 14616697.77 | -1891751.22 | 19358971.43 | 1641434.57 | 2026-07-01 | Forecasted savings in Earthwork, Planting, and Contingency
24-8-014-ashasc | 24-3-014-ashasc | SDC-ASH-A Shell & Core LLO | Ted Satterthwaite | 107203530 | 3647705 | 110851235 | 109065580.13 | 53166656.34 | 1261537.87 | 110327118 | 524117 | 2026-07-01
24-8-052-ashadh1 | 24-3-052-ashadh1 | SDC-ASH-A Data Hall 1 LLO | Ted Satterthwaite | 90413597 | 1390989 | 91804586 | 90505302.64 | 32054022.88 | 1191615.82 | 91696918.46 | 107667.54 | 2026-06-24
24-8-053-ashadh2 | 24-3-053-ashadh2 | SDC-ASH-A Data Hall 2 LLO | Ted Satterthwaite | 87254515 | 1363004 | 88617519 | 87331739.54 | 17642785.96 | 1208860.52 | 88540600.06 | 76918.94 | 2026-08-27
n/a | 25-5-125-ashab1 | SDC-ASH-AB-1 Oracle 3MW Fit Out TI | Ted Satterthwaite | 5999535 | 0 | 5999535 | 7524119.06 | 2845781.11 | -101701.88 | 7422417.18 | -1422882.18 | 2025-10-31 | Post lease execution scope changes [sub-let cage] and acceleration [6 weeks] request by Tenant. Lease service order pending to increase budget.
SDC Quincy
24-8-029-quie1si | 24-7-029-quie1si | SDC-QUI-E1 Site LLO | Connie Taylor | 425433 | 83379 | 508812 | 514718.68 | 199364.64 | -3525.98 | 511192.7 | -2380.7 | 2025-11-01 | Over budget in Civil design
24-8-030-quie1sc | 24-7-030-quie1sc | SDC-QUI-E1 Shell & Core LLO | Connie Taylor | 789930 | 6671 | 796601 | 790974.91 | 692095.33 | 2105.43 | 793080.34 | 3520.66 | 2025-11-01
24-8-031-quie1dh | 24-7-031-quie1dh | SDC-QUI-E1 9MW Data Hall LLO | Connie Taylor | 85715034 | 2653846 | 88368880 | 86808061.7 | 79651437.29 | 2158887.17 | 88966948.87 | -598068.87 | 2025-11-01 | Over-run due to: switch Zinc batteries to VRLA, CX Mgr, Safety, Security, Plumbing, Insepctions.
25-8-131-quie6 | 25-7-131-quie6 | SDC-QUI-E6 Zoho Office Exp LLO | Connie Taylor | 81046 | 5692 | 86738 | 16097.08 | 13207.08 | 70640.92 | 86738 | 0 | 2025-10-31
25-8-132-quic | 25-7-132-quic | SDC-QUI-C Juniper Office to Storage Conversion LLO | Connie Taylor | 410443 | 17787 | 428230 | 20258.24 | 11908.24 | 407971.76 | 428230 | 0 | 2025-12-31
n/a | 24-5-072-quie1 | SDC-QUI-E1MWH23_EX2 Security Design TI | Connie Taylor | 150498 | 0 | 150498 | 131180.87 | 126683.37 | 19310.9 | 150491.77 | 6.23 | 2026-01-14
n/a | 24-5-076-quie1 | SDC-QUI-E1MWH23_EX2 COLO Fit Out Design TI | Connie Taylor | 279522 | 0 | 279522 | 247253.06 | 166253.06 | 34983.66 | 282236.72 | -2714.72 | 2025-10-31 | Over-charged SCI labor
n/a | 25-5-093-quie1 | SDC-QUI-E1MWH23_EX2 COLO RoIP Design TI | Connie Taylor | 47310 | 0 | 47310 | 46772.21 | 25272.21 | 4073.69 | 50845.9 | -3535.9 | 2025-03-01 | Wrong estimate template was used. No mark-up and tax applied.
n/a | 25-5-097-quie1 | SDC-QUI-E1MWH23_EX2 HAC TI | Connie Taylor | 1179872 | 0 | 1179872 | 1029130.33 | 1029130.33 | 150741.67 | 1179872 | 0 | 2025-05-31
n/a | 25-5-099-quie1 | SDC-QUI-E1MWH23_EX2 Core Design Changes TI | Connie Taylor | 370831 | 0 | 370831 | 319599.06 | 318866.06 | 47668.05 | 367267.11 | 3563.89 | 2025-05-30
n/a | 25-5-100-quie1 | SDC-QUI-E1MWH23_EX2 Security TI | Connie Taylor | 1433166 | 0 | 1433166 | 1205531.8 | 665952.46 | 224331.88 | 1429863.68 | 3302.32 | 2025-12-31
n/a | 25-5-101-quie1 | SDC-QUI-E1MWH23_EX2 Electrical TI | Connie Taylor | 3375527 | 0 | 3375527 | 2732946.01 | 2277687.01 | 642580.99 | 3375527 | 0 | 2025-10-31
n/a | 25-5-102-quie1 | SDC-QUI-E1MWH23_EX2 Telecom TI | Connie Taylor | 973976 | 0 | 973976 | 793177.29 | 625813.29 | 180798.71 | 973976 | 0 | 2025-10-31
n/a | 25-5-114-quie1 | SDC-QUI-E1MWH23_EX2 Appliances TI | Connie Taylor | 15309 | 0 | 15309 | 14528.69 | 14528.69 | 468.5 | 14997.19 | 311.81 | 2025-07-31
n/a | 25-5-115-quie1 | SDC-QUI-E1MWH23_EX2 HAC Panels TI FINAL | Connie Taylor | 51747 | 0 | 51747 | 45040 | 0 | 6707 | 51747 | 0 | 2025-07-31
n/a | 25-5-119-quie1 | SDC-QUI-E1MWH23_EX2 RoIP Install TI | Connie Taylor | 266619 | 0 | 266619 | 218151.98 | 102403.87 | 48467.02 | 266619 | 0 | 2025-07-31
n/a | 25-5-121-quie1 | SDC-QUI-E1MWH23_EX2 Security Camera Rough-In TI | Connie Taylor | 59841 | 0 | 59841 | 52109.59 | 52109.59 | 7713.22 | 59822.81 | 18.19 | 2025-07-31
n/a | 25-1-127-quia1 | SDC-QUI-A1 Juniper HAC Assessment | Connie Taylor | 852 | 0 | 852 | 638 | 0 | 214 | 852 | 0 | 2025-09-30
n/a | 25-5-135-quie1 | SDC-QUI-E1 MWH23-EX2 16 SPV to MMR TI | Connie Taylor | 79980 | 0 | 79980 | 0 | 0 | 79980 | 79980 | 0 | 2025-11-30
n/a | 25-5-136-quie1 | SDC-QUI-E1 MWH23-EX2 Reprogram Camera TI | Connie Taylor | 21351 | 0 | 21351 | 17823 | 0 | 3528 | 21351 | 0 | 2025-10-15
n/a | 25-5-137-quie1 | SDC-QUI-E1 Generator Damage Insurance Claim | Connie Taylor | 0 | 0 | 0 | 0 | 0 | 170965 | 170965 | 0 |  | Insurance Claim: Equipment failure caused downstream damage to generator
n/a | 25-1-142-quie6 | SDC-QUI-E6 Zoho 500kW Exp TI | Connie Taylor | 788613 | 0 | 788613 | 0 | 0 | 788613 | 788613 | 0 | 2026-02-28
SDC Columbia
22-8-712 | 22-7-712 | SDC-COL-D3 Data Hall Build LLO | Max Jones | 30903749 | 1459858 | 32363607 | 30419978.67 | 30412676.29 | 351995.34 | 30771974.01 | 1591632.99 | 2025-06-30 | Actively working to close this job out
23-8-717 | 23-7-717 | SDC-COL-Bldg E Design | Max Jones | 70731 | 1785844 | 1856575 | 1540834.55 | 1434336.8 | 0 | 1540834.55 | 315740.45 | 2025-09-30
24-8-010-colb | 24-7-010-colb | SDC-COL-B Costco 735kW Exp LLO | Max Jones | 6094503 | 240497 | 6335000 | 6231185.82 | 4737683.19 | -1477793.21 | 4753392.61 | 1581607.39 | 2025-08-06 | Actively working to close this job out
24-8-023-cole1dh | 24-7-023-cole1dh | SDC-COL-E2 9MW Data Hall 1 LLO | Max Jones | 87276455 | 2362512 | 89638967 | 87705763.58 | 26777358.31 | 1528843.82 | 89234607.4 | 404359.6 | 2026-10-30
24-8-050-colesi | 24-7-050-colesi | SDC-COL-E Site LLO | Max Jones | 12375443 | 392829 | 12768272 | 12620566.85 | 5817746.13 | 79964.41 | 12700531.26 | 67740.74 | 2026-02-16
24-8-051-colesc | 24-7-051-colesc | SDC-COL-E Shell & Core LLO | Max Jones | 41289894 | 1340626 | 42630520 | 41553720.25 | 21452011.43 | 909367.14 | 42463087.39 | 167432.61 | 2026-02-16
25-8-117-cole1 | 25-7-117-cole1 | SDC-COL-E1 9MW Data Hall LLO | Max Jones | 79791150 | 3522608 | 83313758 | 80673838.67 | 11156748.34 | 2677605.81 | 83351444.48 | -37686.48 | 2027-10-01 | Over budget in Civil design (unbudgeted)
24-8-079-colb12 | 24-7-079-colb12 | SDC-COL-B Data Hall 1 & 2 Tier 3 Conversion | Max Jones | 14051592 | 848024 | 14899616 | 14796549.17 | 10938112.22 | -75470.47 | 14721078.7 | 178537.3 | 2025-11-01
25-8-134-colb3 | 25-7-134-colb3 | SDC-COL-B3 Crowdstrike RPP LLO | Max Jones | 867838 | 8798 | 876636 | 0 | 0 | 876636 | 876636 | 0 | 2025-12-31
SDC Seattle
23-8-719 | 23-7-719 | SDC-SEA-43 6MW Data Hall Build | Glenn Parry | 64265925 | 1451808 | 65717733 | 65308212.23 | 57789543.06 | -2155160.82 | 63153051.41 | 2564681.59 | 2025-12-01
24-8-077-sdc53 | 24-7-077-sdc53 | SDC-SEA-53 UPS Replacement LLO | Glenn Parry | 2499592 | 74970 | 2574562 | 2555807.57 | 1882487.08 | 18754.43 | 2574562 | 0 | 2025-08-01
25-8-095-sdc42 | 25-7-095-sdc42 | SDC-SEA-42 D2 Chiller Install LLO | Glenn Parry | 1368352 | 35347 | 1403699 | 1388524.28 | 641593.28 | 15174.72 | 1403699 | 0 | 2025-11-30
25-8-096-sdc4 | 25-7-096-sdc4 | SDC-SEA-7 Bldg Design | Marcus McFarland | 128460 | 2270132 | 2398592 | 1387535.38 | 99300.38 | 1011056.62 | 2398592 | 0 | 2026-02-28
25-8-123-sdchq | 25-7-123-sdchq | SDC-IGW-B SDC HQ 2nd Fl Expansion | Sergio Ortega | 2150616 | 393412 | 2544028 | 7943.6 | 7943.6 | 2536084.4 | 2544028 | 0 | 2026-03-20
25-8-128-sdc5 | 25-7-128-sdc5 | SDC-SEA-4201 Peg Tech LLO (Raksmart) | Glenn Parry | 12616 | 71 | 12687 | 0 | 0 | 12687 | 12687 | 0 | 2025-10-01
25-8-130-sdc5 | tbd | SDC-SEA-5 Elevator Modernization Design | Glenn Parry | 0 | 22845 | 22845 | 35901.85 | 17881.85 | 0 | 35901.85 | -13056.85 | 2025-12-31 | Cost over-run in elevator consultant. Ph 2 construction scope pending.
n/a | 24-5-074-sdc4203 | SDC-SEA-4203 Tencent Decommissioning | Glenn Parry | 189963 | 0 | 189963 | 78064.7 | 76152.6 | 94767.55 | 172832.25 | 17130.75 | 2025-08-31
n/a | 24-1-061-ige03 | SDC-SEA-3 Prov PHCC Pharmacy HVAC TI | Paul Swanson | 3584022 | 0 | 3584022 | 2336577.16 | 1759694.64 | 577820.56 | 2914397.72 | 669624.28 | 2025-10-13 | phased
n/a | 25-5-118-sdc4 | SDC-SEA-4 Service Now Tile Replacement | Glenn Parry | 80800 | 0 | 80800 | 65916.19 | 65916.19 | 14265 | 80181.19 | 618.81 | 2025-08-31
n/a | 25-5-129-sdc5 | SDC-SEA-4201 Peg Tech TI (RAKsmart) | Glenn Parry | 70499 | 0 | 70499 | 50896.45 | 44481.45 | 19602.55 | 70499 | 0 | 2025-10-01
n/a | 25-5-138-sdc4301 | SDC-SEA-4301 Akamai Exp TI | Glenn Parry | 2593666 | 0 | 2593666 | 0 | 0 | 2593666 | 2593666 | 0 | 2026-03-20
SDC Texas
22-8-402 | 22-4-402 | SDC-AUS-A Shell & Core LLO | Jon Hunter | 52991920 | 1131690 | 54123610 | 53780691.04 | 53780514.32 | 8900.09 | 53789591.13 | 334018.87 | 2024-05-31 | Actively working to close these jobs out
23-8-406 | 23-4-406 | SDC-AUS-B Design LLO | Jeff Giguiere | 0 | 5674706 | 5674706 | 5342222.44 | 4759565.89 | 332483.56 | 5674706 | 0 | 2025-08-31
24-8-015-ausa | 24-5-015-ausa | SDC-AUS-A EDC Equip Fire Insurance Claim | Jon Hunter | 14560627.91 |  | 14560627.91 | 13479809.99 | 13253114.34 | 1080817.69 | 14560627.68 | 0.23 | 2025-09-30
24-8-022-ausa11 | 24-4-022-ausa11 | SDC-AUS-A11 9MW Data Hall | Jon Hunter | 83003431 | 2608667 | 85612098 | 84881539.49 | 70062426.25 | 2340923.51 | 87222463 | -1610365 | 2025-12-31 | Includes some JS sub costs. Move to JS Fit Out job once approved.
24-8-055-ausa12 | 24-4-055-ausa12 | SDC-AUS-A12 TACC 15MW LLO | Jon Hunter | 46939658 | 1782466 | 48722124 | 48620176.14 | 36923141.1 | 101434.04 | 48721610.18 | 513.82 | 2026-01-31
25-8-091-ausamck | 25-4-091-ausamck | SDC-AUS-A McKinstry Office LLO | Alfred Ngang | 389186 | 45742 | 434928 | 516896.2 | 443625.06 | -65800.7 | 451095.5 | -16167.5 | 2025-08-31 | Cost over-run due to unaccounted low voltage scope + new transformer
25-8-085-ausbsi | 25-4-085-ausbsi | SDC-AUS-B Site LLO | Jeff Giguiere | 23389074 | 363646 | 23752720 | 23564671.39 | 6869977.91 | 188048.61 | 23752720 | 0 | 2027-06-30
25-8-086-ausbsc | 25-4-086-asubsc | SDC-AUS-B Shell & Core LLO | Jeff Giguiere | 92455808 | 910872 | 93366680 | 92557313.49 | 23179366.48 | 809366.51 | 93366680 | 0 | 2027-06-30
25-8-087-ausb35 | 25-4-087-ausb35 | SDC-AUS-B Data Hall B35 LLO | Jeff Giguiere | 94250488 | 1256078 | 95506566 | 94253817.65 | 1165264.04 | 1252748.35 | 95506566 | 0 | 2027-12-31
25-8-088-ausb36 | 25-4-088-ausb36 | SDC-AUS-B Data Hall B36 LLO | Jeff Giguiere | 93565670 | 1250658 | 94816328 | 93567455.49 | 536882.9 | 1248872.51 | 94816328 | 0 | 2028-03-31
n/a | 24-5-058-austacc | SDC-AUS-A12 TACC 15MW TI | Jon Hunter | 6495658 | 0 | 6495658 | 5167748.01 | 2008466.62 | 1327909.99 | 6495658 | 0 | 2026-03-01
n/a | 25-5-104-ausa23 | SDC-AUS-A23 Lambda POD 0-6 TI | Jon Hunter | 50901 | 0 | 50901 | 8466.62 | 8466.62 | 42434.38 | 50901 | 0 | 2025-12-31
n/a | 25-5-107-ausa11 | SDC-AUS-A11 Jane St NRC 1 TI | Jon Hunter | 703405 | 0 | 703405 | 621654.22 | 63249.28 | 81750.78 | 703405 | 0 | 2025-12-31
n/a | 25-5-122-ausa11 | SDC-AUS-A11 Jane St NRC 2 Fit Out TI | Jon Hunter | 7982842 | 0 | 7982842 | 6474349.93 | 3688998.06 | 1504492.07 | 7978842 | 4000 | 2025-12-31 | This job will ultimately turn into the Fit Out TI job once NRC 3 is approved
n/a | 25-5-124-ausa | SDC-AUS-A AWS 2MW Expansion Design TI | Jon Hunter | 191249 | 0 | 191249 | 167437.96 | 4297.96 | 23811.04 | 191249 | 0 | 2025-08-31
SDC Manhattan
21-8-601 | 21-6-601 | SDC-NY 7th Fl Demo/Abatement/Common Area Const | Lou Vigorito | 2358593 | 1009193 | 3367786 | 3279809.6 | 3184427.17 | 48185.38 | 3327994.98 | 39791.02 | 2025-03-31
23-8-604 | 23-6-604 | SDC-NY 7th Fl Jane Street Turnkey Data Center Exp | Lou Vigorito | 34944119 | 1836932 | 36781051 | 36982239.61 | 30684366.97 | -4073056.91 | 32909182.7 | 3871868.3 | 2025-03-31
24-8-006-nyc375 | 24-6-006-nyc375 | SDC-NY Local Law 11 Remediation/Window Wall Repairs | Lou Vigorito | 2184648 | 185637 | 2370285 | 2376715.67 | 2341043.31 | 11886.06 | 2388601.73 | -18316.73 | 2025-03-31 | Window Wall Legal Fees not budgeted. Offset with contingency
25-8-105-ny375 | 25-6-105-ny375 | SDC-NY Cooling Tower 6 Study | Lou Vigorito | 38147 | 152334 | 190481 | 139638 | 37195 | 50843 | 190481 | 0 | 2025-10-02
25-8-113-nyc375 | 25-6-113-ny375 | SDC-NY NYSERDA Heat Recovery Study | Lou Vigorito | 10253 | 70859 | 81112 | 29255 | 7688.75 | 51857 | 81112 | 0 | 2025-09-30
SDC Umatilla
24-8-028-uma | n/a | SDC-UMA-Site Substation | Marcus McFarland | 0 | 43253310 | 43253310 | 12395969.87 | 12395969.87 | 28637310 | 43256279.74 | -2969.74 | 2029-12-31 | Legal fees
24-8-066-umades | 24-9-066-umades | SDC-UMA-Building Design Phase 1 | Bryce Drury | 387717 | 4082640 | 4470357 | 3269098.65 | 2385801.26 | 1201258.35 | 4470357 | 0 | 2025-09-01
SDC Other
22-7-711 | 22-7-711 | SCI Advanced Purchase Program (SDCP Prefund) | Marcus/Dave Buckner | 201501066.73 | 0 | 201501066.73 | 159978958.78 | 10307004.16 | 94053673.95 | 201501066.73 | 0 | 2028-12-31
24-8-011-sdcmal | 24-7-011-sdcmal | IGQ 80-Acre Malaga Property Due Diligence | Clete Casper | 0 | 7668821.7 | 7668821.7 | 7573557.44 | 7569057.44 | 0 | 7573557.44 | 95264.26 | 2025-03-31
24-8-054-sdcsan | 24-7-054-sdcsan | SDC San Marcos TX 207 Acre Due Diligence | Clete Casper | 49677 | 400323 | 450000 | 587156.89 | 572041.89 | 0 | 587156.89 | -137156.89 | 2025-03-31 | Transmission Planning Study $200K (Pedernales Electric Coop)
25-8-098-sdcpflu | 25-7-098-sdcpflu | SDC Pflugerville TX Due Diligence | Clete Casper | 25000 | 590000 | 615000 | 28806.33 | 13306.33 | 586193.67 | 615000 | 0 | 2026-09-18
25-8-112-sdcmt | 25-7-112-sdcmt | SDC MT Butte Connections 606-Acre Due Diligence | Clete Casper | 25000 | 380000 | 405000 | 126600 | 2500 | 277700 | 404300 | 700 | 2025-12-15
25-8-120-sdcmt | 25-7-120-sdcmt | SDC MT Anacoda ARCO 816-Acre Due Diligence | Clete Casper | 0 | 210000 | 210000 | 196500 | 45182.99 | 13500 | 210000 | 0 | 2028-01-01
25-8-133-sdcind | 25-7-133-sdcind | SDC IN Decatur Tech Park Due Diligence | Clete Casper | 25000 | 555500 | 580500 | 6225.01 | 6225 | -6225.01 | 580500 | 0 | 2026-06-30
Sabey Commercial
16-8-494 | 18-2-201 | Cherry Hill Medical Pavilion (18th Ave) | James Conley | 4440079 | 4068386 | 8508465 | 8256452.37 | 8080995.54 | -140340.49 | 8116111.88 | 392353.12 | 2025-12-31 | Zayo needs to submit final bill. SCL charges in dispute. May remove power poles.
24-8-032-jeffgar | 24-2-032-jeffgar | Jefferson Publc Garage Resurfacing LLO | Paul Swanson | 321265 | 1980065 | 2301330 | 2253845.23 | 2238846.39 | -10987.4 | 2242857.83 | 58472.17 | 2025-08-31
24-8-033-jeffgar | 24-2-033-jeffgar | Jefferson Tower Garage Elevator Modernization | Paul Swanson | 158196 | 1143378 | 1301574 | 1266444.3 | 1084715.17 | -13425.73 | 1253018.57 | 48555.43 | 2026-05-18
24-8-034-jamtow | 24-2-034-jamtow | James Tower Elevator Modernization | Paul Swanson | 214231 | 1508330 | 1722561 | 1707904.41 | 1334877.47 | 9490.08 | 1717394.49 | 5166.51 | 2026-01-31
24-8-057-jamtow | 24-2-057-jamtow | James Tower Elevator Cab Finishes | Paul Swanson | 148768 | 2329 | 151097 | 150381.02 | 75569.16 | -4599.92 | 145781.1 | 5315.9 | 2025-01-20
25-8-084-scorphq | 25-2-084-scorphq | Sabey 4th Floor Remodel | Sergio Ortega | 293455 | 393500 | 686955 | 368791.2 | 363089.48 | 318163.8 | 686955 | 0 | 2025-12-31
|  | TOTAL |  | 1566116397.64 | 116357349.7 | 1682473747.34 | 1571048026.8 | 728299750.12 | 147993537.15 | 1669313497.82 | 13331214.52
Distribution List:
Dale Spencer
Marcus McFarland
Max Wright
Dave Buckner
Johhny Miles
Javier Zavala
Justin Feiock
Alex Turla

## Proj. Cost Analysis
ProjectCostAnalysis
Group By 1 = Job
Property = .sci,.sdcp,.scorp,.sprop,.snp
Category Tree = ysi_JobCost
Period = Sep 2025
Job Status = In Progress,Completed
Job | Job Description | Original Budget | Budget Revision | Revised Budget | Current Commitment | Billed To Date | Paid to Date | Variance | Cost to Complete | Projected Final Cost | Variance
|  | (A) | (B) | (C = A+B) | (D) | (E) | (F) | (G = C-D) | (H = I-D) | (I) | (J = C-I)
00-00-000 | CC Reconciliations-SCI | 0 | 0 | 0 | -470.04 | -470.04 | -470.04 | 470.04 | 470.04 | 0 | 0
16-8-494 | CH Medical Pavilion | 1273272 | 7235193 | 8508465 | 8256452.37 | 8080995.54 | 8081135.27 | 252012.63 | -140340.49 | 8116111.88 | 392353.12
18-2-201 | CH Medical Pavilion | 145656 | 4294423 | 4440079 | 3774611.28 | 3772174.66 | 3766509.6 | 665467.72 | 456599.38 | 4231210.66 | 208868.34
21-6-601 | IGM 7th Fl Demo/Common Area Const | 564370 | 1794223 | 2358593 | 2160684.26 | 2119394.66 | 2154244.66 | 197908.74 | 123784.21 | 2284468.47 | 74124.53
21-8-601 | IGM 7th Fl Demo & Common Area Const | 736786 | 2631000 | 3367786 | 3279809.6 | 3184427.17 | 3109992.9 | 87976.4 | 48185.38 | 3327994.98 | 39791.02
22-3-303 | IGA-B Quad 1 6MW DH AB1-1 & AB1-2 | 44728039 | 0 | 44728039 | 40847044.05 | 40493288.74 | 40492156.91 | 3880994.95 | 2093613.71 | 42940657.76 | 1787381.24
22-4-402 | SDC Austin Bldg A Shell & Core | 44222236 | 8769684 | 52991920 | 50628555.68 | 50628553.3 | 50635403.27 | 2363364.32 | 2540524.3 | 53169079.98 | -177159.98
22-7-711 | SCI Advanced Purchase Program | 22735000 | 178766066.73 | 201501066.73 | 107447392.78 | 10307004.16 | 19288013.54 | 94053673.95 | 94053673.95 | 201501066.73 | 0
22-7-712 | IGC-D Data Hall D3 Build-Out | 16183434 | 14720315 | 30903749 | 26747920.29 | 26720416.41 | 26691908.12 | 4155828.71 | 3074898.47 | 29822818.76 | 1080930.24
22-8-402 | SDC Austin Bldg A Shell & Core DEV | 46027533 | 8096077 | 54123610 | 53780691.04 | 53780514.32 | 53773514.68 | 342918.96 | 8900.09 | 53789591.13 | 334018.87
22-8-502 | IGA Building A Design 54MW DC DEV | 1970836 | 3044174 | 5015010 | 4876694.19 | 4673491.84 | 4667431.84 | 138315.81 | 0 | 4876694.19 | 138315.81
22-8-503 | IGA-B Quad 1 6MW DH AB1-1 & AB1-2 | 45413939 | 0 | 45413939 | 42753459.68 | 42738674.68 | 42816409.63 | 2660479.32 | 378266.34 | 43131726.02 | 2282212.98
22-8-712 | IGC-D Data Hall D3 Build-Out DEV | 16305962 | 16057645 | 32363607 | 30419978.67 | 30412676.29 | 30404641.52 | 1943628.33 | 351995.34 | 30771974.01 | 1591632.99
23-5-532 | AUS-A 2MW Lab & Office Build TI | 455258 | 9104604 | 9559862 | 8838988.71 | 8848606.02 | 8407612.32 | 720873.29 | 720873.29 | 9559862 | 0
23-6-604 | IGM 7th Fl Jane Street Exp LLO | 35463335 | -519216 | 34944119 | 28336902.63 | 28311233.24 | 27822584.54 | 6607216.37 | 3369242.04 | 31706144.67 | 3237974.33
23-7-705 | IGQ-Echo E5 & E6 9MW Data Halls | 71659860 | 7014764 | 78674624 | 70289241.06 | 70186444.37 | 70127021.67 | 8385382.94 | 7312996.41 | 77602237.47 | 1072386.53
23-7-713 | SDC 5203B Providence Restoration | 143704 | 35632 | 179336 | 155509.3 | 155205.79 | 155205.79 | 23826.7 | 24634.49 | 180143.79 | -807.79
23-7-717 | SDC-COL Bldg E Design Thru Permit | 70731 | 0 | 70731 | 66914.39 | 66914.39 | 66914.39 | 3816.61 | 9606.3 | 76520.69 | -5789.69
23-7-719 | SDC 43 6MW Data Hall Build | 51969 | 64213956 | 64265925 | 52671519.44 | 50662350 | 46769990.48 | 11594405.56 | 9057693.65 | 61729213.09 | 2536711.91
23-8-406 | SDC Austin Bldg. B Design DEV | 2673731 | 3000975 | 5674706 | 5342222.44 | 4759565.89 | 4710365.89 | 332483.56 | 332483.56 | 5674706 | 0
23-8-604 | IGM 7th Fl Jane Street Exp LLO | 36781051 | 0 | 36781051 | 36982239.61 | 30684366.97 | 29375459.86 | -201188.61 | -4073056.91 | 32909182.7 | 3871868.3
23-8-714 | IGQ-E Data Hall 5 Design Thru IFC | 607209 | 451487 | 1058696 | 1077552.47 | 965399.45 | 964472.82 | -18856.47 | -106173 | 971379.47 | 87316.53
23-8-715 | IGC DCPUD 100MW Feasibility Study | 25000 | 20943800 | 20968800 | 20786300 | 2286300 | 25000 | 182500 | -20786300 | 0 | 20968800
23-8-717 | SDC-COL Bldg E Design Thru Permit | 1856575 | 0 | 1856575 | 1540834.55 | 1434336.8 | 1419685.49 | 315740.45 | 0 | 1540834.55 | 315740.45
23-8-719 | SDC 43 6MW Data Hall Build | 727260 | 64990473 | 65717733 | 65308212.23 | 57789543.06 | 53252587.37 | 409520.77 | -2155160.82 | 63153051.41 | 2564681.59
24-1-061-ige03 | IGE-03 PHCC Pharmacy HVAC TI | 3682537 | -98515 | 3584022 | 2336577.16 | 1759694.64 | 1657537.85 | 1247444.84 | 577820.56 | 2914397.72 | 669624.28
24-1-067-nyc375 | NY SpaceX Antenna Feasibility Study | 6128 | 0 | 6128 | 5053.46 | 5053.46 | 5053.46 | 1074.54 | 1074.54 | 6128 | 0
24-1-081-rtp | RTP-Providence Ste 200 Storage Rms | 9806 | 0 | 9806 | 3463.01 | 3463.01 | 3463.01 | 6342.99 | 582.94 | 4045.95 | 5760.05
24-2-032-jeffgar | Jefferson Tower Garage Resurfacing | 321265 | 0 | 321265 | 237333.15 | 237001.07 | 234761.91 | 83931.85 | 62709.49 | 300042.64 | 21222.36
24-2-033-jeffgar | Jefferson Garage Elevator Mod | 158196 | 0 | 158196 | 97179.05 | 94938.41 | 83811.79 | 61016.95 | 50451.15 | 147630.2 | 10565.8
24-2-034-jamtow | James Tower Elevator Modernization | 214231 | 0 | 214231 | 144057.07 | 139892.24 | 138981.65 | 70173.93 | 67111.89 | 211168.96 | 3062.04
24-2-057-jamtow | James Tower Elevator Finishes | 148768 | 0 | 148768 | 132835.55 | 63389.05 | 60446.47 | 15932.45 | 21990.93 | 154826.48 | -6058.48
24-3-013-ashasi | SDC-ASH-A Site LLO | 7978740 | 12260543 | 20239283 | 16711668.17 | 13141520.13 | 10677335.13 | 3527614.83 | 1798597.89 | 18510266.06 | 1729016.94
24-3-014-ashasc | SDC-ASH-A Shell & Core LLO | 24437404 | 82766126 | 107203530 | 90122915.08 | 49039803.15 | 39966651.34 | 17080614.92 | 16535769.31 | 106658684.39 | 544845.61
24-3-052-ashadh1 | SDC-ASH-A35 9MW Data Hall LLO | 95036400 | -4622803 | 90413597 | 77546409.37 | 30404832.5 | 14703651.54 | 12867187.63 | 13083494.09 | 90629903.46 | -216306.46
24-3-053-ashadh2 | SDC-ASH-A23 9MW Data Hall LLO | 95036400 | -7781885 | 87254515 | 73996838.27 | 16708575.49 | 14270478.8 | 13257676.73 | 13198396.79 | 87195235.06 | 59279.94
24-4-022-ausa11 | SDC-AUS-A11 9MW Data Hall Build | 76204796 | 6798635 | 83003431 | 85056953.51 | 65721337.26 | 53145138.18 | -2053522.51 | 266879.36 | 85323832.87 | -2320401.87
24-4-055-ausa12 | SDC-AUS-A12 15MW TACC Data Hall LLO | 46019246 | 920412 | 46939658 | 43346385.8 | 34357699.37 | 27531075.97 | 3593272.2 | 3593272.2 | 46939658 | 0
24-4-063-ausawb | SDC-AUS-A WB Engineers Office LLO | 412761 | 0 | 412761 | 362083.64 | 362083.37 | 346797.8 | 50677.36 | 18629.18 | 380712.82 | 32048.18
24-5-015-ausa | SDC-AUS-A EDC Equip Fire Ins Claim | 5661751.11 | 7991457.8 | 13653208.91 | 13479809.99 | 13253114.34 | 12649574.46 | 173398.92 | 1080817.69 | 14560627.68 | -907418.77
24-5-047-sdc04 | SDC-SEA-04 Google COLO 5 TI | 1045150 | 0 | 1045150 | 865659.79 | 865659.79 | 865353.53 | 179490.21 | 145145.19 | 1010804.98 | 34345.02
24-5-058-austacc | SDC-AUS-A12 TACC 15MW TI | 10368505 | -3872847 | 6495658 | 5167748.01 | 2008466.62 | 1245542.78 | 1327909.99 | 1327909.99 | 6495658 | 0
24-5-066-dhs | DHS Weapons Cleaning Rm Renovation | 105890 | 0 | 105890 | 83918.07 | 83918.07 | 83918.07 | 21971.93 | 17173 | 101091.07 | 4798.93
24-5-072-quie1 | SDC-QUI-E1 MWH23-EX2 Security Des | 150498 | 0 | 150498 | 131180.87 | 126683.37 | 126676.16 | 19317.13 | 19310.9 | 150491.77 | 6.23
24-5-073-quie1 | SDC-QUI-E1 MWH23-EX2 Office Design | 94381 | 0 | 94381 | 82354.49 | 45354.49 | 45354.49 | 12026.51 | 12137.31 | 94491.8 | -110.8
24-5-074-sdc4203 | SDC-4203 Tencent Decommissioning | 189963 | 0 | 189963 | 78064.7 | 76152.6 | 76152.6 | 111898.3 | 94767.55 | 172832.25 | 17130.75
24-5-075-quie1 | SDC-QUI-E1 MWH23-EX2 IDF Walls TI | 376960 | 0 | 376960 | 328980.59 | 328965.77 | 315771.27 | 47979.41 | 47869.06 | 376849.65 | 110.35
24-5-076-quie1 | SDC-QUI-E1 MWH23-EX2 COLO Design | 279522 | 0 | 279522 | 247253.06 | 166253.06 | 166253.06 | 32268.94 | 34983.66 | 282236.72 | -2714.72
24-5-083-ashibm | SDC-ASH-B IBM Office & Storage TI | 203145 | 0 | 203145 | 184374.24 | 128383.24 | 128383.24 | 18770.76 | 9926 | 194300.24 | 8844.76
24-6-006-nyc375 | SDC-NY-375 Local Law 11 Remediation | 10584 | 2174064 | 2184648 | 2047746.44 | 2047746.44 | 1775029.89 | 136901.56 | 136787.76 | 2184534.2 | 113.8
24-7-010-colb | SDC-COL-B Costco 735kW Exp LLO | 6094503 | 0 | 6094503 | 4071641.78 | 4071116.68 | 3927772.33 | 2022861.22 | 542587.48 | 4614229.26 | 1480273.74
24-7-023-cole1dh | SDC-COL-E2 9MW Data Hall LLO | 80870674 | 6405781 | 87276455 | 68541656.62 | 23738194.27 | 21519380.19 | 18734798.38 | 18348050.43 | 86889707.05 | 386747.95
24-7-029-quie1si | SDC-QUI-E1 Site LLO | 450433 | -25000 | 425433 | 340133.69 | 99942.69 | 48817.69 | 85299.31 | 85299.31 | 425433 | 0
24-7-030-quie1sc | SDC-QUI-E1 Shell & Core LLO | 916060 | -126130 | 789930 | 642799.18 | 605335.18 | 567249.75 | 147130.82 | 145064.16 | 787863.34 | 2066.66
24-7-031-quie1dh | SDC-QUI-E1 9MW Data Hall | 84451147 | 1263887 | 85715034 | 77314619.83 | 71282972.95 | 63606838.29 | 8400414.17 | 9119094.69 | 86433714.52 | -718680.52
24-7-039-sdc53 | SDC-SEA-53 RTU Replacement | 1990704 | 0 | 1990704 | 1672646.96 | 1568905.96 | 1494369.51 | 318057.04 | 269684.17 | 1942331.13 | 48372.87
24-7-050-colesi | SDC-COL-E Site LLO | 13676848 | -1301405 | 12375443 | 9146864.45 | 4905299.55 | 3756688.53 | 3228578.55 | 3167786.13 | 12314650.58 | 60792.42
24-7-051-colesc | SDC-COL-E Shell & Core LLO | 28865087 | 12424807 | 41289894 | 31427082.77 | 18643602.2 | 15180142.95 | 9862811.23 | 9754830.63 | 41181913.4 | 107980.6
24-7-054-sdcsan | SDC San Marcos TX Due Diligence | 49677 | 0 | 49677 | 41039.35 | 41039.35 | 41039.35 | 8637.65 | 8637.65 | 49677 | 0
24-7-077-sdc53 | SDC-SEA-53 UPS Replacement | 2499592 | 0 | 2499592 | 1946666.55 | 1734800.06 | 1569654.34 | 552925.45 | 554925.45 | 2501592 | -2000
24-7-079-colb12 | SDC-COL-B DH 1&2 Tier 3 Conversion | 12056062 | 1995530 | 14051592 | 11636950.16 | 9660888.67 | 8201065.44 | 2414641.84 | 2237144.31 | 13874094.47 | 177497.53
24-8-006-nyc375 | SDC-NY-375 Local Law 11 Remediation | 76341 | 2293944 | 2370285 | 2376715.67 | 2341043.31 | 2030811.82 | -6430.67 | 11886.06 | 2388601.73 | -18316.73
24-8-010-colb | SDC-COL-B Costco 735kW Exp LLO | 6335000 | 0 | 6335000 | 6231185.82 | 4737683.19 | 4548148.76 | 103814.18 | -1477793.21 | 4753392.61 | 1581607.39
24-8-011-sdcmal | SDC Malaga 80-Acre Due Diligence | 7668821.7 | 0 | 7668821.7 | 7573557.44 | 7569057.44 | 7563591.94 | 95264.26 | 0 | 7573557.44 | 95264.26
24-8-013-ashasi | SDC-ASH-A Site LLO DEV | 8222833 | 12777573 | 21000406 | 21250722.65 | 14616697.77 | 11769754.8 | -250316.65 | -1891751.22 | 19358971.43 | 1641434.57
24-8-014-ashasc | SDC-ASH-A Shell & Core LLO DEV | 25229090 | 85622145 | 110851235 | 109065580.13 | 53166656.34 | 42967075.6 | 1785654.87 | 1261537.87 | 110327118 | 524117
24-8-015-ausa | SDC-AUS-A EDC Equip Fire Ins Claim | 0 | 0 | 0 | 14037418.23 | 14021729.23 | 14010856.01 | -14037418.23 | 66655.86 | 14104074.09 | -14104074.09
24-8-022-ausa11 | SDC-AUS-A11 9MW Data Hall DEV | 78704993 | 6907105 | 85612098 | 84881539.49 | 70062426.25 | 57989140.5 | 730558.51 | 2340923.51 | 87222463 | -1610365
24-8-023-cole1dh | SDC-COL-E2 9MW Data Hall LLO | 83669477 | 5969490 | 89638967 | 87705763.58 | 26777358.31 | 23901496.77 | 1933203.42 | 1528843.82 | 89234607.4 | 404359.6
24-8-028-uma | SDC-UMA-Site Substation | 515000 | 42738310 | 43253310 | 12395969.87 | 12395969.87 | 12395969.87 | 30857340.13 | 28637310 | 41033279.87 | 2220030.13
24-8-029-quie1si | SDC-QUI-E1 Site LLO DEV | 508812 | 0 | 508812 | 514718.68 | 199364.64 | 137637.02 | -5906.68 | -3525.98 | 511192.7 | -2380.7
24-8-030-quie1sc | SDC-QUI-E1 Shell & Core DEV | 922731 | -126130 | 796601 | 790974.91 | 692095.33 | 642622.54 | 5626.09 | 2105.43 | 793080.34 | 3520.66
24-8-031-quie1dh | SDC-QUI-E1 9MW Data Hall DEV | 87069701 | 1299179 | 88368880 | 86808061.7 | 79651437.29 | 74281086.22 | 1560818.3 | 2158887.17 | 88966948.87 | -598068.87
24-8-032-jeffgar | Jefferson Tower Garage Resurfacing | 2301330 | 0 | 2301330 | 2253845.23 | 2238846.39 | 2158962.76 | 47484.77 | -10987.4 | 2242857.83 | 58472.17
24-8-033-jeffgar | Jefferson Garage Elevator Mod | 1301574 | 0 | 1301574 | 1266444.3 | 1084715.17 | 922284.27 | 35129.7 | -13425.73 | 1253018.57 | 48555.43
24-8-034-jamtow | James Tower Elevator Modernization | 1722561 | 0 | 1722561 | 1707904.41 | 1334877.47 | 1223973.38 | 14656.59 | 9490.08 | 1717394.49 | 5166.51
24-8-039-sdc53 | SDC-SEA-53 RTU Replacement | 2029530 | 0 | 2029530 | 2019329.02 | 1854312.89 | 1774131.29 | 10200.98 | -38441.02 | 1980888 | 48642
24-8-050-colesi | SDC-COL-E Site LLO DEV | 14226825 | -1458553 | 12768272 | 12620566.85 | 5817746.13 | 4436963.79 | 147705.15 | 79964.41 | 12700531.26 | 67740.74
24-8-051-colesc | SDC-COL-E Shell & Core LLO DEV | 30185484 | 12445036 | 42630520 | 41553720.25 | 21452011.43 | 17107624.74 | 1076799.75 | 909367.14 | 42463087.39 | 167432.61
24-8-052-ashadh1 | SDC-ASH-A35 9MW Data Hall LLO DEV | 98635062 | -6830476 | 91804586 | 90505302.64 | 32054022.88 | 15021504.75 | 1299283.36 | 1191615.82 | 91696918.46 | 107667.54
24-8-053-ashadh2 | SDC-ASH-A23 9MW Data Hall LLO DEV | 98635062 | -10017543 | 88617519 | 87331739.54 | 17642785.96 | 14345637.24 | 1285779.46 | 1208860.52 | 88540600.06 | 76918.94
24-8-054-sdcsan | SDC San Marcos TX Due Diligence | 450000 | 0 | 450000 | 587156.89 | 572041.89 | 570926.96 | -137156.89 | 0 | 587156.89 | -137156.89
24-8-055-ausa12 | SDC-AUS-A12 15MW Data Hall LLO | 47527226 | 1194898 | 48722124 | 48620176.14 | 36923141.1 | 29297068.23 | 101947.86 | 101434.04 | 48721610.18 | 513.82
24-8-057-jamtow | James Tower Elevator Finishes | 151097 | 0 | 151097 | 150381.02 | 75569.16 | 72220.91 | 715.98 | -4599.92 | 145781.1 | 5315.9
24-8-063-ausawb | SDC-AUS-A WB Engineers Office LLO | 439671 | 0 | 439671 | 396085.77 | 396085.77 | 377690.26 | 43585.23 | 525.24 | 396611.01 | 43059.99
24-8-066-umades | SDC-UMA-Building Design Phase 1 DEV | 2248841 | 2221516 | 4470357 | 3269098.65 | 2385801.26 | 2086377.65 | 1201258.35 | 1201258.35 | 4470357 | 0
24-8-077-sdc53 | SDC-SEA-53 UPS Replacement | 2574562 | 0 | 2574562 | 2555807.57 | 1882487.08 | 1607746.17 | 18754.43 | 18754.43 | 2574562 | 0
24-8-079-colb12 | SDC-COL-B DH 1&2 Tier 3 Conversion | 12391188 | 2508428 | 14899616 | 14796549.17 | 10938112.22 | 9121983.31 | 103066.83 | -75470.47 | 14721078.7 | 178537.3
24-9-066-umades | SDC-UMA-Building Design Phase 1 | 115312 | 272405 | 387717 | 182185.64 | 181741.21 | 181374.58 | 205531.36 | 205531.36 | 387717 | 0
25-1-106-cold3 | SDC-COL-D3 Epic 730kW Exp TI | 671779 | 212452 | 884231 | 733435.66 | 733435.66 | 629357.06 | 150795.34 | 113536.76 | 846972.42 | 37258.58
25-1-127-quia1 | SDC-QUI-A1 Juniper HAC Assessment | 852 | 0 | 852 | 638 | 0 | 0 | 214 | 214 | 852 | 0
25-1-140-sdc5 | SDC House UPS Replacement | 144053 | 0 | 144053 | 0 | 0 | 0 | 144053 | 0 | 0 | 144053
25-1-141-sdc5 | Security Office & IDF HVAC Replace | 106565 | 0 | 106565 | 0 | 0 | 0 | 106565 | 0 | 0 | 106565
25-1-142-quie6 | SDC-QUI-E6 Zoho 500kW Exp TI | 788613 | 0 | 788613 | 0 | 0 | 0 | 788613 | 788613 | 788613 | 0
25-2-084-scorphq | Sabey Corp 4th Fl Office Remodel | 293455 | 0 | 293455 | 167975.71 | 140816.66 | 133947.46 | 125479.29 | 125479.29 | 293455 | 0
25-4-085-ausbsi | SDC-AUS-B Site LLO | 23389074 | 0 | 23389074 | 17751011.48 | 6516469.29 | 3556126.38 | 5638062.52 | 5638062.52 | 23389074 | 0
25-4-086-asubsc | SDC-AUS-B Shell & Core LLO | 92455808 | 0 | 92455808 | 35659990.83 | 22036335.62 | 15385891.41 | 56795817.17 | 56795817.17 | 92455808 | 0
25-4-087-ausb35 | SDC-AUS-B DH B35 LLO | 94250488 | 0 | 94250488 | 11306520.94 | 1106606.01 | 1106606.01 | 82943967.06 | 82943967.06 | 94250488 | 0
25-4-088-ausb36 | SDC-AUS-B DH B36 LLO | 93565670 | 0 | 93565670 | 11466661.04 | 509616.58 | 509616.58 | 82099008.96 | 82099008.96 | 93565670 | 0
25-4-091-ausamck | SDC-AUS-A McKinstry Office LLO | 389186 | 0 | 389186 | 387547.89 | 385524.89 | 367586.19 | 1638.11 | 21244.69 | 408792.58 | -19606.58
25-4-094-ausa2 | SDC-AUS-A2 SDC Office Expansion | 29731 | 0 | 29731 | 17598.31 | 17598.31 | 17598.31 | 12132.69 | 879.92 | 18478.23 | 11252.77
25-5-093-quie1 | SDC-QUI-E1 MWH23-EX2 RoIP Design TI | 47310 | 0 | 47310 | 46772.21 | 25272.21 | 25272.21 | 537.79 | 4073.69 | 50845.9 | -3535.9
25-5-097-quie1 | SDC-QUI-E1 MWH23-EX2 HAC TI | 1179872 | 0 | 1179872 | 1029130.33 | 1029130.33 | 818158.36 | 150741.67 | 150741.67 | 1179872 | 0
25-5-099-quie1 | SDC-QUI-E1 MWH23-EX2 Core Changes | 370831 | 0 | 370831 | 319599.06 | 318866.06 | 229693.59 | 51231.94 | 47668.05 | 367267.11 | 3563.89
25-5-100-quie1 | SDC-QUI-E1 MWH23-EX2 Security TI | 1433166 | 0 | 1433166 | 1205531.8 | 665952.46 | 410815.47 | 227634.2 | 224331.88 | 1429863.68 | 3302.32
25-5-101-quie1 | SDC-QUI-E1 MWH23-EX2 Electrical TI | 3375527 | 0 | 3375527 | 2732946.01 | 2277687.01 | 1293544.16 | 642580.99 | 642580.99 | 3375527 | 0
25-5-102-quie1 | SDC-QUI-E1 MWH23-EX2 Telecom TI | 973976 | 0 | 973976 | 793177.29 | 625813.29 | 176985.24 | 180798.71 | 180798.71 | 973976 | 0
25-5-103-cold2 | SDC-COL-D2 VULTR Cage & Office TI | 208099 | 0 | 208099 | 163257.85 | 157424.1 | 150887.56 | 44841.15 | 29719.1 | 192976.95 | 15122.05
25-5-104-ausa23 | SDC-AUS-A23 Lambda POD 0-6 TI | 50901 | 0 | 50901 | 8466.62 | 8466.62 | 8466.62 | 42434.38 | 42434.38 | 50901 | 0
25-5-107-ausa11 | SDC-AUS-A11 Jane St NRC-1 UPS Equip | 703405 | 0 | 703405 | 621654.22 | 63249.28 | 4631.9 | 81750.78 | 81750.78 | 703405 | 0
25-5-108-ausa23 | AUS080 Rack Filling Station | 9718 | 0 | 9718 | 2678.63 | 2678.63 | 2678.63 | 7039.37 | 364.84 | 3043.47 | 6674.53
25-5-114-quie1 | SDC-QUI-E1 MWH23-EX2 Appliances TI | 15309 | 0 | 15309 | 14528.69 | 14528.69 | 14528.69 | 780.31 | 468.5 | 14997.19 | 311.81
25-5-115-quie1 | SDC-QUI-E1 MWH23-EX2 HAC Panels TI | 51747 | 0 | 51747 | 45040 | 0 | 0 | 6707 | 6707 | 51747 | 0
25-5-118-sdc4 | SDC-04 Service Now Tile Replacement | 80800 | 0 | 80800 | 65916.19 | 65916.19 | 2689.19 | 14883.81 | 14265 | 80181.19 | 618.81
25-5-119-quie1 | SDC-QUI-E1 MWH23-EX2 RoIP Install | 266619 | 0 | 266619 | 218151.98 | 102403.87 | 17645.48 | 48467.02 | 48467.02 | 266619 | 0
25-5-121-quie1 | SDC-QUI-E1 MWH23-EX2 Camera TI | 59841 | 0 | 59841 | 52109.59 | 52109.59 | 20051.49 | 7731.41 | 7713.22 | 59822.81 | 18.19
25-5-122-ausa11 | SDC-AUS-A11 Jane Street Fit Out TI | 2522364 | 5460478 | 7982842 | 6474349.93 | 3688998.06 | 75160.66 | 1508492.07 | 1504492.07 | 7978842 | 4000
25-5-124-ausa | SDC-AUS-A 2MW Exp Design TI | 191249 | 0 | 191249 | 167437.96 | 4297.96 | 783.96 | 23811.04 | 23811.04 | 191249 | 0
25-5-125-ashab1 | SDC-ASH-AB1-1 Oracle 3MW Fit Out | 5999535 | 0 | 5999535 | 7524119.06 | 2845781.11 | 17764.43 | -1524584.06 | -101701.88 | 7422417.18 | -1422882.18
25-5-129-sdc5 | SDC-SEA-4201 Peg Tech TI | 70499 | 0 | 70499 | 50896.45 | 44481.45 | 633.45 | 19602.55 | 19602.55 | 70499 | 0
25-5-135-quie1 | SDC-QUI-E1 MWH23-EX2 16 SPV to MMR | 79980 | 0 | 79980 | 0 | 0 | 0 | 79980 | 79980 | 79980 | 0
25-5-136-quie1 | SDC-QUI-E1 MWH23 Reprogram Cameras | 21351 | 0 | 21351 | 17823 | 0 | 0 | 3528 | 3528 | 21351 | 0
25-5-137-quie1 | SDC-QUI-E1 Genset Damage Ins Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170965 | 170965 | -170965
25-5-138-sdc4301 | SDC-SEA-4301 Akamai Exp. TI | 2593666 | 0 | 2593666 | 0 | 0 | 0 | 2593666 | 2593666 | 2593666 | 0
25-6-105-ny375 | SDC-NY-375 Cooling Tower 6 Study | 38147 | 0 | 38147 | 0 | 0 | 0 | 38147 | 38147 | 38147 | 0
25-6-113-ny375 | SDC-NY NYSERDA Heat Recovery Study | 10253 | 0 | 10253 | 0 | 0 | 0 | 10253 | 10253 | 10253 | 0
25-7-095-sdc42 | SDC-SEA-5 42 D-2 Chiller Install | 1368352 | 0 | 1368352 | 1060554.57 | 550356.22 | 104090.49 | 307797.43 | 307797.43 | 1368352 | 0
25-7-096-sdc4 | SDC-SEA-07 Expansion Due Diligence | 14017 | 114443 | 128460 | 14911.9 | 14911.9 | 14911.9 | 113548.1 | 113548.1 | 128460 | 0
25-7-098-sdcpflu | SDC Pflugerville TX Due Diligence | 25000 | 0 | 25000 | 7898.97 | 7898.97 | 7898.97 | 17101.03 | 17101.03 | 25000 | 0
25-7-112-sdcmt | SDC MT Connections Due Diligence | 25000 | 0 | 25000 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 0
25-7-117-cole1 | SDC-COL-E1 9MW Data Hall | 79791150 | 0 | 79791150 | 54278270.06 | 9637852.31 | 8816035.91 | 25512879.94 | 25510579.7 | 79788849.76 | 2300.24
25-7-123-sdchq | SDC-SEA-B SDC HQ Office Exp | 2150616 | 0 | 2150616 | 0 | 0 | 0 | 2150616 | 2150616 | 2150616 | 0
25-7-126-quia1 | SDC-QUI-A1 Juniper 500kVA PDU LLO | 352234 | 0 | 352234 | 295658.56 | 0 | 0 | 56575.44 | 56575.44 | 352234 | 0
25-7-128-sdc5 | SDC-SEA-4201 Peg Tech LLO | 12616 | 0 | 12616 | 9301.72 | 9301.72 | 316.72 | 3314.28 | 3311 | 12612.72 | 3.28
25-7-131-quie6 | SDC-QUI-E6 Zoho Office Exp LLO | 81046 | 0 | 81046 | 64229.06 | 9522.56 | 169.06 | 16816.94 | 16816.94 | 81046 | 0
25-7-132-quic | SDC-QUI-C Juniper Off-Storage Conv | 410443 | 0 | 410443 | 354851 | 4651 | 4651 | 55592 | 55592 | 410443 | 0
25-7-133-sdcind | SDC Decatur Tech Park Due Diligence | 25000 | 0 | 25000 | 0 | 0 | 0 | 25000 | 0 | 0 | 25000
25-7-134-colb3 | SDC-COL-B3 Crowdstrike RPP LLO | 867838 | 0 | 867838 | 778818 | 0 | 0 | 89020 | 89020 | 867838 | 0
25-8-084-scorphq | Sabey Corp 4th Fl Office Remodel | 686955 | 0 | 686955 | 368791.2 | 363089.48 | 343818.61 | 318163.8 | 318163.8 | 686955 | 0
25-8-085-ausbsi | SDC-AUS-B Site LLO | 23752720 | 0 | 23752720 | 23564671.39 | 6869977.91 | 3656173.53 | 188048.61 | 188048.61 | 23752720 | 0
25-8-086-ausbsc | SDC-AUS-B Shell & Core LLO | 93366680 | 0 | 93366680 | 92557313.49 | 23179366.48 | 16109053.94 | 809366.51 | 809366.51 | 93366680 | 0
25-8-087-ausb35 | SDC-AUS-B DH B35 LLO | 95506566 | 0 | 95506566 | 94253817.65 | 1165264.04 | 1049070.6 | 1252748.35 | 1252748.35 | 95506566 | 0
25-8-088-ausb36 | SDC-AUS-B DH B36 LLO | 94816328 | 0 | 94816328 | 93567455.49 | 536882.9 | 483373.16 | 1248872.51 | 1248872.51 | 94816328 | 0
25-8-091-ausamck | SDC-AUS-A McKinstry Office LLO | 434928 | 0 | 434928 | 516896.2 | 443625.06 | 443145.06 | -81968.2 | -65800.7 | 451095.5 | -16167.5
25-8-094-ausa2 | SDC-AUS-A2 SDC Office Expansion | 154016 | 0 | 154016 | 118839.74 | 118035.44 | 118035.44 | 35176.26 | 150.59 | 118990.33 | 35025.67
25-8-095-sdc42 | SDC-SEA-5 42 D-2 Chiller Install | 1403699 | 0 | 1403699 | 1388524.28 | 641593.28 | 120938.89 | 15174.72 | 15174.72 | 1403699 | 0
25-8-096-sdc4 | SDC-SEA-07 Expansion Due Diligence | 134498 | 2264094 | 2398592 | 1387535.38 | 99300.38 | 95650.38 | 1011056.62 | 1011056.62 | 2398592 | 0
25-8-098-sdcpflu | SDC Pflugerville TX Due Diligence | 615000 | 0 | 615000 | 28806.33 | 13306.33 | 12806.33 | 586193.67 | 586193.67 | 615000 | 0
25-8-105-ny375 | SDC-NY-375 Cooling Tower 6 Study | 190481 | 0 | 190481 | 139638 | 37195 | 33475.4 | 50843 | 50843 | 190481 | 0
25-8-112-sdcmt | SDC MT Connections Due Diligence | 405000 | 0 | 405000 | 126600 | 2500 | 0 | 278400 | 277700 | 404300 | 700
25-8-113-nyc375 | SDC-NY NYSERDA Heat Recovery Study | 81112 | 0 | 81112 | 29255 | 7688.75 | 7188.75 | 51857 | 51857 | 81112 | 0
25-8-117-cole1 | SDC-COL-E1 9MW Data Hall DEV | 83313758 | 0 | 83313758 | 80673838.67 | 11156748.34 | 9830676.31 | 2639919.33 | 2677605.81 | 83351444.48 | -37686.48
25-8-120-sdcmt | SDC-MT ARCO 816-Acre Due Diligence | 615000 | -405000 | 210000 | 196500 | 45182.99 | 500 | 13500 | 13500 | 210000 | 0
25-8-123-sdchq | SDC-SEA-B SDC HQ Office Exp | 2544028 | 0 | 2544028 | 7943.6 | 7943.6 | 0 | 2536084.4 | 2536084.4 | 2544028 | 0
25-8-126-quia1 | SDC-QUI-A1 Juniper 500kVA PDU LLO | 365872 | 0 | 365872 | 0 | 0 | 0 | 365872 | 365872 | 365872 | 0
25-8-128-sdc5 | SDC-SEA-4201 Peg Tech LLO | 12687 | 0 | 12687 | 0 | 0 | 0 | 12687 | 12687 | 12687 | 0
25-8-130-sdc5 | SDC-SEA-5 Elevator Modernization | 22845 | 0 | 22845 | 35901.85 | 17881.85 | 17881.85 | -13056.85 | 0 | 35901.85 | -13056.85
25-8-131-quie6 | SDC-QUI-E6 Zoho Office Exp LLO | 86738 | 0 | 86738 | 16097.08 | 13207.08 | 2021.61 | 70640.92 | 70640.92 | 86738 | 0
25-8-132-quic | SDC-QUI-C Juniper Off-Storage Conv | 428230 | 0 | 428230 | 20258.24 | 11908.24 | 6599.35 | 407971.76 | 407971.76 | 428230 | 0
25-8-133-sdcind | SDC Decatur Tech Park Due Diligence | 580500 | 0 | 580500 | 6225.01 | 6225 | 6225 | 574274.99 | -6225.01 | 0 | 580500
25-8-134-colb3 | SDC-COL-B3 Crowdstrike RPP LLO | 876636 | 0 | 876636 | 0 | 0 | 0 | 876636 | 876636 | 876636 | 0
Grand Total |  | 2416711712.81 | 697281727.53 | 3113993440.34 | 2574311074.99 | 1422060179.95 | 1248000496.23 | 539682365.35 | 505949834.91 | 3080260909.9 | 33732530.44

## Instructions
Go to Job Cost Analytics report in Yardi
This will need to be split between SDCP and Non-SDCP due to the reports being so big and takes too long to load. DO NOT DISPLAY, instead print to Excel (too much data to Display).
For Non-SDCP
Property: .sci, .sprop,.snp, .scorp
Job Status: In Progress, Completed, Closed
Report: Project Cost Analysis
Group by 1: Job
Upload the excel file to the Proj. Cost Analysis - Non-SDCP tab
For SDCP
Property: .sci, .sdcp
Job Status: In Progress, Completed, Closed
Report: Project Cost Analysis
Group by 1: Job
Upload the excel file to the Proj. Cost Analysis - SDCP tab