## Reports
week_ending | project_title | region | tenant | start_date | scheduled_completion | project_budget | eac | budget_variance | percent_complete | total_trade_workers | work_performed | safety | source
2025-11-01 | James Tower Elevator Mods. 24 2 034 11 1 2025 | Non SDC Projects |  | 2024-09-09 | 2025-11-27 | 1722561 | 1717394 | 5167 | 79 | 7 | Supervision turn over elevator 1 to public, demolition of freighter elevator4 and crane pick | None to report | weekly_project_summary.html
2025-11-01 | Jefferson Garage Elevator Modernization 11 1 2025 | Non SDC Projects |  | 2024-09-09 | 2026-01-12 | 1301574 | 1253019 | 48555 | 69 | 5 | Otis Elevator: Wiring and troubleshooting elevator car. Pre-Final inpection on elevator car. 16D: pre-final smoke alarm test and install wire from elevator car to fire alarm Rm. for emergency call from inside elevator. | None to report | weekly_project_summary.html
2025-11-01 | ASH A 11 01 25 | SDC Ashburn | TBD | 2024-06-10 | 2026-07-09 | 312273746 | 309923608 | 2350138 | 7 | 204 | Jobsite general cleaning, coordination, supervision, safety/quality control, and offside parking maintenance, directing on site truck traffic and site logistics. Cleaning floors and putting up plastic over the windows in preparation for winter. Sealing gaps in preparation of the stair landing pour. Flushing the reclaimed water to the West. Loading out dirt and grading behind the curb with topsoil in the west. Prepping for curb. Backfilling ground loop in the west for DYNA. Continue Inspecting compaction for the backfill of ditches. Taking concrete cylinders for the concrete pours. Continue Inspecting roofing of the building. . Inspecting the 5 chiller platforms for A35. Poured the demands and floor in the West stairwell. Poured the USS and NVS pads in the Northeast yard. Poured curb to the West. Running conduit for the in A35 and A23. Installing hanger for the OH conduit rack in A35and A23.Laying out for priority wall penetrations. Working on temp power for the temporary heaters and freight elevator work. Installing 12" cold water piping for the second floor core. Craning in chilled water piping on the first floor core. Setting pump skids for the adiabatic systems and 5 EDCs on the roof. Installing water piping on the 3rd and 2nd floor to the East and the Core. Installing roof drain piping through the interior of the core. Setting floor drains in slab on grade West. Roughing in core bathrooms. Installing ductwork in the core, verified penetration locations and sizes. Taking delivery of duct work. Installing DOAS ductwork in A35 and A23. Installing DOAS units for A35 on the roof. Installing sprinkler lines in the Core, first floor. Welding out 5 frames for A35 chillers on the roof. Caulking on the inside, outside of the Core and West end of the building. Continue filling control joints in the West with polyurea. Installing conduit in 3rd floor core for low voltage to allow for wall close in. Detailing out the main roof and installing downspouts and wall cap. Finish framing up CRAH openings in A23. Double siding drywall in 3rd floor core and framing walls on the first floor core. Beginning on framing the penthouse. Finished the passenger elevator and meeting on site to go over the freight elevator install. Skim coating precast walls that came on site rough and washing the outside of the building in the attempt to color match. Continuing punchout throughout the building and design modifications Continuing painting the priority walls and the walls behind the CRAHs | None to report | weekly_project_summary.html
2025-11-01 | ASH AB1 11 01 25 | SDC Ashburn | OCI | 2025-09-02 | 2025-12-01 | 5999535 | 7422417 |  | 98 | 9 | Cleaning and supervision Supervision Adding labeling as it comes in. Adding grounding for new rack locations Completed testing on the final 4 fibers. Testing is 100% complete. | None | weekly_project_summary.html
2025-11-01 | AUS 11 Weekly Job Status 11.01.25 | SDC Austin | Jane Street | 2024-10-28 | 2026-02-25 | 85612098 | 87222463 |  | 78 | 68 | General trash clean up and sweeping. Moving material and equipment to facilitate work in progress. Clean and wipe down of EDCs in Yard C. Prestart up and Cx repairs. Drip pan install under CHWP over electrical equipment. OH conduit install and conduit down to electrical gear on the east side. Wire pulling during evening shift and conduit install in electrical mechanical room. Cable bus wire pull in Yard C. | None to report | weekly_project_summary.html
2025-11-01 | AUS 12 Weekly Job Status 11.01.25 | SDC Austin | UT Adv Compute Ctr | 2024-10-28 | 2026-01-30 | 55217782 | 55217268 | 514 | 75 | 35 | General clean up and sweeping of space, checking of dehumidifiers. CHWP install of the Technology loop. Wire pulling for switchgear. Chiller wire terminations on roof. Underground conduit in Yard F for metering on MVS. | None to report | weekly_project_summary.html
2025-11-01 | AUS Building B 11.01.25 | SDC Austin | TBD | 2025-03-24 | 2028-03-05 | 307442294 | 307442294 | 0 | 5 | 44 | Site safety, coordination | None to report | weekly_project_summary.html
2025-11-01 | SDC COL B DATA HALL 1&2 TIER 3 CONVERSION 11.1.25 | SDC Columbia | Crowdstrike | 2025-03-24 | 2025-12-01 | 14899616 | 14721079 | 178537 | 96 | 30 | FINISHED UP DEMO IN CB2, FOCUSED ON BUILDING CHIMNEYS FOR CB3 CX, WILL CONTINUE TO MOVE MATERIAL FROM SITE, SITE MAINTANENCE ASSISTED KBA CB1/2 ATS CX, LBDP CX'D, ASSISTED WITH A/B LINE CX IN CB3 ELECTRICAL ROOM, STARTED CORD CHECKS FOR CB3 CX, | NO INJURIES REPORTED, DAILY MEETINGS ON CX DISCUSSION, LB SHUTDOWN 10/30, SDC/HOLMES WILL LOOK INTO THE ISSUE. | weekly_project_summary.html
2025-11-01 | SDC Columbia 24 7 051 SDC COL E Shell Core LLO 11 1 2025 | SDC Columbia |  | 2025-02-10 | 2026-11-01 | 145037759 | 144398226 | 639533 | 43 | 90 | Contractor safety & coordination, asset & risk management, general conditions, QAQC overview, filled scope gaps, implementing and monitoring supplemental building heat for CE2 & Core Complete layer #1 asphalt, backfill portion of MV duct bank to sub-station, regraded Clemons street project access, excavated loading dock continuous footing Set control for storm water excavation at CE2 yard area and shot existing building (D) edge of asphalt elevation. Worked on MV conduits at CE1 equipment yard & Pangborn substation conduit pathway, completed rough in at electrical and battery rooms roof penetration Re mobed to site & formed reinforced and place (4) canopy spread footings, layout dock for excavator, formed continuous dock footings& received rebar | None to report | weekly_project_summary.html
2025-11-01 | SDC Manhattan Cooling Tower 6 Study 11.1.25 | SDC Manhattan |  | 2025-05-06 |  | 190481 | 190481 | 0 | 5 |  | None to report | N/A | weekly_project_summary.html
2025-11-01 | SDC Manhattan NYSERDA Heat Recovery Study 11.1.25 | SDC Manhattan |  | 2025-06-10 | 2025-11-17 | 81112 | 81112 | 0 | 75 |  | None to report | N/A | weekly_project_summary.html
2025-11-01 | IGQ QUI E1 9MW LLO 11.01.25 | SDC Quincy | Microsoft | 2024-08-21 | 2025-11-01 | 88368880 | 88966949 |  | 99 | 30 | Supervision, Scheduling, site services, MOP reviews, QA/QC. General cleaning. Assisted contractors with material removal out of the building. Worked on Punchlist items. No work. Completed punchlist items. Received fire final. No work. Provided cooling for load on the floor as needed. Supported ABB with troubleshooting UPS-F issues. Supported full burn on UPS-C to burn off the off gassing. Verified time stamps on equipment. Finalized panel schedules and installed phenolics. Supported load on the floor for UPS-R burn for the Industrial Hygienist to take air quality samples. Set scaffold for emissions testing. Dismantled stair tower for roof access and gen after emissions test. Touched up landscaping at the fuel access road. Site safety meeting, site walks and safety audits, new hire orientations. Manage LOTO operations. No work. Repaired down spouts in the electrical yard from trade damage and completed installing the hoods for the LB Kingspan penetrations. No work. Supported emissions testing. No work. No work. No work. No work. No work. Completed issues resolution with UPS-F. | This weeks safety: Hierarchy of controls. | weekly_project_summary.html
2025-11-01 | IGQ QUI E16 ZOHO OFFICE EXPANSION LLO 11.01.25 | SDC Quincy | ZOHO | 2025-09-22 | 2025-10-30 | 86738 | 86738 | 0 | 99 | 5 | Supervision, Scheduling, MOP reviews, QA/QC. General cleaning. On site to install carpet. Discovered that it was the incorrect carpet, decided to install anyway to cover the floor. The correct carpet has been discontinued, we are looking at other sites to see if there is any owner stock available in Washington. On hold until we get the correct material or come up with a alternative. Complete Complete Complete Complete | None to report | weekly_project_summary.html
2025-11-01 | SDC QUI E1 MWH23 EX2 Fit Out TI 11.1.25 | SDC Quincy | Microsoft | 2025-03-10 | 2025-11-01 | 8305549 | 8304597 | 952 | 99 | 23 | Supervising, QA-QC, General cleaning . Unloading trucks and demobilize. No work this week. No work this week. No work this week. No work this week. Finishing grounding, Demobilizing. QA-QC yard cameras as well as pulling security and installing door contact as well as card reader for added 3.0 X 7.0 cmu door. Testing Fiber. Helped convergint. Plugging in the RPDU's for the IDF rows and MOR cabinets in COLO C and D. Demobilizing and cleaning up. Putting red caps on the ends of struts and all threads in COLO C and D. No work this week. No work this week. No work this week. Delivered material for flooring Finishing grounding, Demobilizing. QA-QC yard cameras as well as pulling security and installing door contact as well as card reader for added 3.0 X 7.0 cmu door. Testing Fiber. Helped convergint adjusting cameras. Finished all security . Waiting on 3rd party commissioning to retest. Heirarchy of controls. Security commissioning and continue demobilizing. | None to report | weekly_project_summary.html
2025-11-01 | SDC QUI Juniper Office Storage Conversion 11.1.25 | SDC Quincy | Juniper | 2025-09-22 | 2025-12-12 | 428230 | 428230 | 0 | 22 | 5 | Supervision. Scheduling. Unloaded flooring and stocked in juniper space. Walked with SDC to review MOP. | None to report | weekly_project_summary.html
2025-11-01 | SDC SEA 53 UPS Replacement 11.1.2025 | SDC Seattle |  | 2025-06-24 | 2025-11-04 | 2574562 | 2574562 | 0 | 97 | 7 | Supervision Safe Off Old Electrical Feeders. No Activity. No Activity. No Activity. No Activity. Re-Build & Test 2 Trip Switches. | Tool Box Talk - PPE | weekly_project_summary.html
2025-11-01 | SDC SEA SDC42 Chiller 11.1.2025 | SDC Seattle |  | 2025-09-16 | 2025-11-21 | 1403699 | 1403699 | 0 | 82 | 5 | Supervision No Activity. Insulate Chilled Water Piping. Set Up To Flush & Clean New CW Piping. No Activity. No Activity. No Activity. | Tool Box Talk - PPE | weekly_project_summary.html
2025-11-01 | SEA Providence Pharmacy HVAC TI 11 01 2025 | SDC Seattle | PROVIDENCE | 2025-03-10 | 2026-01-23 | 3584022 | 2914398 | 669624 | 70 | 18 | Supervision Continue installing new duct work Start painting patches and ceilings Remove outlets for FRP install Structural framing on under side of roof for supply and return duct. / Drywall Roof duct stands and supply and return duct. Build toe kicks for mill work Run control wires Take down scaffolding Crane pick 2 units to roof | Weekly safety inspection and meeting performed by Rob Pritchett | weekly_project_summary.html
2025-11-01 | IGE SDC 43 6MW 110125 |  | Akamai | 2024-09-03 | 2025-12-12 | 65717733 | 63153051 | 2564682 | 94 | 35 | clean up, dump trash, daily site walks and sub coordination, Cx Alloy L3 checklists, run loadbanks for Cx fuel susytems controls tie in, daytank / pump start up, Cx Alloy checklists, Munters onside for Sycool startup L4s, sunbelt working on integration w/ daiken, Vertiv CRACs L4s | no incidents, weekly safety topic - Using Halotron FEs | weekly_project_summary.html

## SubcontractorActivity
week_ending | project_title | region | company | craft | trade_workers | source
2025-11-01 | ASH A 11 01 25 | SDC Ashburn | Advanced Caulking | Caulker | 6 | weekly_project_summary.html
2025-11-01 | ASH A 11 01 25 | SDC Ashburn | Beltway Paving | Concrete | 19 | weekly_project_summary.html
2025-11-01 | ASH A 11 01 25 | SDC Ashburn | Cascade Steel | Misc. Metals | 5 | weekly_project_summary.html
2025-11-01 | ASH A 11 01 25 | SDC Ashburn | Dyna | Electric | 56 | weekly_project_summary.html
2025-11-01 | ASH A 11 01 25 | SDC Ashburn | ECS Mid-Atlantic | Inspections | 2 | weekly_project_summary.html
2025-11-01 | ASH A 11 01 25 | SDC Ashburn | Independence Ex | Civil | 14 | weekly_project_summary.html
2025-11-01 | ASH A 11 01 25 | SDC Ashburn | KONE | Elevator | 2 | weekly_project_summary.html
2025-11-01 | ASH A 11 01 25 | SDC Ashburn | PCI | Framer/Drywall | 48 | weekly_project_summary.html
2025-11-01 | ASH A 11 01 25 | SDC Ashburn | Power Solutions | Low Voltage, Thermostats | 7 | weekly_project_summary.html
2025-11-01 | ASH A 11 01 25 | SDC Ashburn | Sabey Construction | Contractor | 6 | weekly_project_summary.html
2025-11-01 | ASH A 11 01 25 | SDC Ashburn | Southland | Pipe Fitters | 13 | weekly_project_summary.html
2025-11-01 | ASH A 11 01 25 | SDC Ashburn | Southland | Plumbing | 4 | weekly_project_summary.html
2025-11-01 | ASH A 11 01 25 | SDC Ashburn | Southland | Sheet Metal | 5 | weekly_project_summary.html
2025-11-01 | ASH A 11 01 25 | SDC Ashburn | Southland | Sprinkler | 8 | weekly_project_summary.html
2025-11-01 | ASH A 11 01 25 | SDC Ashburn | TECTA | Roofing | 9 | weekly_project_summary.html
2025-11-01 | ASH AB1 11 01 25 | SDC Ashburn | CCCI | Low Voltage | 2 | weekly_project_summary.html
2025-11-01 | ASH AB1 11 01 25 | SDC Ashburn | CPG | TI GC | 2 | weekly_project_summary.html
2025-11-01 | ASH AB1 11 01 25 | SDC Ashburn | NOVA | Electrical | 3 | weekly_project_summary.html
2025-11-01 | ASH AB1 11 01 25 | SDC Ashburn | Sabey Construction | GC | 2 | weekly_project_summary.html
2025-11-01 | AUS 11 Weekly Job Status 11.01.25 | SDC Austin | Big State Electric - BSE | Electrical | 50 | weekly_project_summary.html
2025-11-01 | AUS 11 Weekly Job Status 11.01.25 | SDC Austin | Chasco | Concrete Restoration |  | weekly_project_summary.html
2025-11-01 | AUS 11 Weekly Job Status 11.01.25 | SDC Austin | Mckinstry - McK | Mechanical | 6 | weekly_project_summary.html
2025-11-01 | AUS 11 Weekly Job Status 11.01.25 | SDC Austin | Mckinstry - McK | Demo |  | weekly_project_summary.html
2025-11-01 | AUS 11 Weekly Job Status 11.01.25 | SDC Austin | Medel | Drywall Finish/Paint |  | weekly_project_summary.html
2025-11-01 | AUS 11 Weekly Job Status 11.01.25 | SDC Austin | PCI | Strut Grid / ACT | 4 | weekly_project_summary.html
2025-11-01 | AUS 11 Weekly Job Status 11.01.25 | SDC Austin | PCI | Framing / GWB |  | weekly_project_summary.html
2025-11-01 | AUS 11 Weekly Job Status 11.01.25 | SDC Austin | PCI | Doors |  | weekly_project_summary.html
2025-11-01 | AUS 11 Weekly Job Status 11.01.25 | SDC Austin | Prestige | Flooring |  | weekly_project_summary.html
2025-11-01 | AUS 11 Weekly Job Status 11.01.25 | SDC Austin | QES | EDCs | 4 | weekly_project_summary.html
2025-11-01 | AUS 11 Weekly Job Status 11.01.25 | SDC Austin | SWMCO | Specialty Sub |  | weekly_project_summary.html
2025-11-01 | AUS 11 Weekly Job Status 11.01.25 | SDC Austin | Sabey | GC | 4 | weekly_project_summary.html
2025-11-01 | AUS 11 Weekly Job Status 11.01.25 | SDC Austin | TBD | Fireproofing |  | weekly_project_summary.html
2025-11-01 | AUS 11 Weekly Job Status 11.01.25 | SDC Austin | TBD | D/F/H |  | weekly_project_summary.html
2025-11-01 | AUS 11 Weekly Job Status 11.01.25 | SDC Austin | Tindall | Precast |  | weekly_project_summary.html
2025-11-01 | AUS 12 Weekly Job Status 11.01.25 | SDC Austin | Big State Electric - BSE | Electrical | 16 | weekly_project_summary.html
2025-11-01 | AUS 12 Weekly Job Status 11.01.25 | SDC Austin | Chasco | Concrete |  | weekly_project_summary.html
2025-11-01 | AUS 12 Weekly Job Status 11.01.25 | SDC Austin | ECS | Special Inspections |  | weekly_project_summary.html
2025-11-01 | AUS 12 Weekly Job Status 11.01.25 | SDC Austin | McKinstry - McK | Fire Sprinklers | 2 | weekly_project_summary.html
2025-11-01 | AUS 12 Weekly Job Status 11.01.25 | SDC Austin | Mckinstry - McK | Mechanical | 8 | weekly_project_summary.html
2025-11-01 | AUS 12 Weekly Job Status 11.01.25 | SDC Austin | Medel | Paint |  | weekly_project_summary.html
2025-11-01 | AUS 12 Weekly Job Status 11.01.25 | SDC Austin | PCI | Strut Grid / ACT |  | weekly_project_summary.html
2025-11-01 | AUS 12 Weekly Job Status 11.01.25 | SDC Austin | PCI | Framing / GWB | 4 | weekly_project_summary.html
2025-11-01 | AUS 12 Weekly Job Status 11.01.25 | SDC Austin | Prestige | Flooring | 4 | weekly_project_summary.html
2025-11-01 | AUS 12 Weekly Job Status 11.01.25 | SDC Austin | Sabey | GC | 1 | weekly_project_summary.html
2025-11-01 | AUS 12 Weekly Job Status 11.01.25 | SDC Austin | Seimens | Fire Detection |  | weekly_project_summary.html
2025-11-01 | AUS 12 Weekly Job Status 11.01.25 | SDC Austin | TBD | Fireproofing |  | weekly_project_summary.html
2025-11-01 | AUS 12 Weekly Job Status 11.01.25 | SDC Austin | TBD | Low Volt |  | weekly_project_summary.html
2025-11-01 | AUS 12 Weekly Job Status 11.01.25 | SDC Austin | TBD | D/F/H |  | weekly_project_summary.html
2025-11-01 | AUS 12 Weekly Job Status 11.01.25 | SDC Austin | Ventana | Glazing |  | weekly_project_summary.html
2025-11-01 | AUS Building B 11.01.25 | SDC Austin | AO Services | Trenching | 5 | weekly_project_summary.html
2025-11-01 | AUS Building B 11.01.25 | SDC Austin | Big State Electric - BSE | Electrical |  | weekly_project_summary.html
2025-11-01 | AUS Building B 11.01.25 | SDC Austin | CMP | Steel |  | weekly_project_summary.html
2025-11-01 | AUS Building B 11.01.25 | SDC Austin | Chasco | Grading | 14 | weekly_project_summary.html
2025-11-01 | AUS Building B 11.01.25 | SDC Austin | ECS | Special Inspections |  | weekly_project_summary.html
2025-11-01 | AUS Building B 11.01.25 | SDC Austin | Kent | Concrete | 16 | weekly_project_summary.html
2025-11-01 | AUS Building B 11.01.25 | SDC Austin | McKinstry - McK | Fire Sprinklers |  | weekly_project_summary.html
2025-11-01 | AUS Building B 11.01.25 | SDC Austin | Mckinstry - McK | Mechanical |  | weekly_project_summary.html
2025-11-01 | AUS Building B 11.01.25 | SDC Austin | Medel | Taping / Painting |  | weekly_project_summary.html
2025-11-01 | AUS Building B 11.01.25 | SDC Austin | PCI | Framing / GWB |  | weekly_project_summary.html
2025-11-01 | AUS Building B 11.01.25 | SDC Austin | Sabey | GC | 1 | weekly_project_summary.html
2025-11-01 | AUS Building B 11.01.25 | SDC Austin | Seimens | Fire Detection |  | weekly_project_summary.html
2025-11-01 | AUS Building B 11.01.25 | SDC Austin | TBD | Fireproofing |  | weekly_project_summary.html
2025-11-01 | AUS Building B 11.01.25 | SDC Austin | TBD | D/F/H |  | weekly_project_summary.html
2025-11-01 | AUS Building B 11.01.25 | SDC Austin | Tindall | Precast | 8 | weekly_project_summary.html
2025-11-01 | IGE SDC 43 6MW 110125 |  | Barclay Dean | D/F/H |  | weekly_project_summary.html
2025-11-01 | IGE SDC 43 6MW 110125 |  | Cochran | Cameras/Security | 1 | weekly_project_summary.html
2025-11-01 | IGE SDC 43 6MW 110125 |  | Expert Drywall | Framing / GWB | 2 | weekly_project_summary.html
2025-11-01 | IGE SDC 43 6MW 110125 |  | Glumac | CX | 2 | weekly_project_summary.html
2025-11-01 | IGE SDC 43 6MW 110125 |  | Holmes Electric | Electrical | 10 | weekly_project_summary.html
2025-11-01 | IGE SDC 43 6MW 110125 |  | Holmes LV | Low Volt |  | weekly_project_summary.html
2025-11-01 | IGE SDC 43 6MW 110125 |  | Mckinstry | Mechanical | 14 | weekly_project_summary.html
2025-11-01 | IGE SDC 43 6MW 110125 |  | NC / CAT | Generators | 2 | weekly_project_summary.html
2025-11-01 | IGE SDC 43 6MW 110125 |  | Praetorian | Electrical Testing | 1 | weekly_project_summary.html
2025-11-01 | IGE SDC 43 6MW 110125 |  | Sabey | GC | 2 | weekly_project_summary.html
2025-11-01 | IGE SDC 43 6MW 110125 |  | Snyder Roofing | Roofing |  | weekly_project_summary.html
2025-11-01 | IGE SDC 43 6MW 110125 |  | Suppression Systems | Fire Detection |  | weekly_project_summary.html
2025-11-01 | IGE SDC 43 6MW 110125 |  | Tbar | Strut Grid / ACT |  | weekly_project_summary.html
2025-11-01 | IGE SDC 43 6MW 110125 |  | Viking | Fire Sprinklers |  | weekly_project_summary.html
2025-11-01 | IGE SDC 43 6MW 110125 |  | WPI | Paint / Raised Floor | 1 | weekly_project_summary.html
2025-11-01 | IGQ QUI E1 9MW LLO 11.01.25 | SDC Quincy | All Valley Sheet Metal | Sheet Metal | 2 | weekly_project_summary.html
2025-11-01 | IGQ QUI E1 9MW LLO 11.01.25 | SDC Quincy | Holmes Electric | Electrical | 10 | weekly_project_summary.html
2025-11-01 | IGQ QUI E1 9MW LLO 11.01.25 | SDC Quincy | Hudson Bay | Insulator |  | weekly_project_summary.html
2025-11-01 | IGQ QUI E1 9MW LLO 11.01.25 | SDC Quincy | IE | EDC |  | weekly_project_summary.html
2025-11-01 | IGQ QUI E1 9MW LLO 11.01.25 | SDC Quincy | IEM | IE Vendor |  | weekly_project_summary.html
2025-11-01 | IGQ QUI E1 9MW LLO 11.01.25 | SDC Quincy | McKinstry | Mechanical |  | weekly_project_summary.html
2025-11-01 | IGQ QUI E1 9MW LLO 11.01.25 | SDC Quincy | McKinstry | Fire Protection | 1 | weekly_project_summary.html
2025-11-01 | IGQ QUI E1 9MW LLO 11.01.25 | SDC Quincy | McKinstry | Sheet Metal | 1 | weekly_project_summary.html
2025-11-01 | IGQ QUI E1 9MW LLO 11.01.25 | SDC Quincy | McKinstry | Mechanical Cx | 3 | weekly_project_summary.html
2025-11-01 | IGQ QUI E1 9MW LLO 11.01.25 | SDC Quincy | NC Power | Generator Tech | 1 | weekly_project_summary.html
2025-11-01 | IGQ QUI E1 9MW LLO 11.01.25 | SDC Quincy | PCI | Carpentry | 3 | weekly_project_summary.html
2025-11-01 | IGQ QUI E1 9MW LLO 11.01.25 | SDC Quincy | Praetorian | NETA Testing |  | weekly_project_summary.html
2025-11-01 | IGQ QUI E1 9MW LLO 11.01.25 | SDC Quincy | Sabey | GC | 4 | weekly_project_summary.html
2025-11-01 | IGQ QUI E1 9MW LLO 11.01.25 | SDC Quincy | Shield of Armor | Safety | 2 | weekly_project_summary.html
2025-11-01 | IGQ QUI E1 9MW LLO 11.01.25 | SDC Quincy | Tripoint | Civil | 3 | weekly_project_summary.html
2025-11-01 | IGQ QUI E16 ZOHO OFFICE EXPANSION LLO 11.01.25 | SDC Quincy | Holmes Electric | Electrical |  | weekly_project_summary.html
2025-11-01 | IGQ QUI E16 ZOHO OFFICE EXPANSION LLO 11.01.25 | SDC Quincy | MQI | Carpet Installer | 1 | weekly_project_summary.html
2025-11-01 | IGQ QUI E16 ZOHO OFFICE EXPANSION LLO 11.01.25 | SDC Quincy | McKinstry | Sheet Metal |  | weekly_project_summary.html
2025-11-01 | IGQ QUI E16 ZOHO OFFICE EXPANSION LLO 11.01.25 | SDC Quincy | PCI | Carpentry | 2 | weekly_project_summary.html
2025-11-01 | IGQ QUI E16 ZOHO OFFICE EXPANSION LLO 11.01.25 | SDC Quincy | Sabey | GC | 2 | weekly_project_summary.html
2025-11-01 | James Tower Elevator Mods. 24 2 034 11 1 2025 | Non SDC Projects | 16D LLC | Custom Elevator Fabrication |  | weekly_project_summary.html
2025-11-01 | James Tower Elevator Mods. 24 2 034 11 1 2025 | Non SDC Projects | Chinook | Elevator Interior |  | weekly_project_summary.html
2025-11-01 | James Tower Elevator Mods. 24 2 034 11 1 2025 | Non SDC Projects | Otis Elevator | Elevator Modernization | 5 | weekly_project_summary.html
2025-11-01 | James Tower Elevator Mods. 24 2 034 11 1 2025 | Non SDC Projects | Sabey | GC | 1 | weekly_project_summary.html
2025-11-01 | James Tower Elevator Mods. 24 2 034 11 1 2025 | Non SDC Projects | Sea. Elevator inspect. | Inspection |  | weekly_project_summary.html
2025-11-01 | James Tower Elevator Mods. 24 2 034 11 1 2025 | Non SDC Projects | Shield of Armor Safety | Safety | 1 | weekly_project_summary.html
2025-11-01 | Jefferson Garage Elevator Modernization 11 1 2025 | Non SDC Projects | Chinook Elevator | Elevator Interiors |  | weekly_project_summary.html
2025-11-01 | Jefferson Garage Elevator Modernization 11 1 2025 | Non SDC Projects | D 16 | elevator inspection | 2 | weekly_project_summary.html
2025-11-01 | Jefferson Garage Elevator Modernization 11 1 2025 | Non SDC Projects | Otis Elevator | Elevator Modernization | 2 | weekly_project_summary.html
2025-11-01 | Jefferson Garage Elevator Modernization 11 1 2025 | Non SDC Projects | Sabey | GC | 1 | weekly_project_summary.html
2025-11-01 | Jefferson Garage Elevator Modernization 11 1 2025 | Non SDC Projects | Todd Folden | Elevator consultant |  | weekly_project_summary.html
2025-11-01 | Jefferson Garage Elevator Modernization 11 1 2025 | Non SDC Projects | West Coast Flooring | Carpet installers |  | weekly_project_summary.html
2025-11-01 | SDC COL B DATA HALL 1&2 TIER 3 CONVERSION 11.1.25 | SDC Columbia | Accelevation | Demo |  | weekly_project_summary.html
2025-11-01 | SDC COL B DATA HALL 1&2 TIER 3 CONVERSION 11.1.25 | SDC Columbia | CBS | Maintenance Testing |  | weekly_project_summary.html
2025-11-01 | SDC COL B DATA HALL 1&2 TIER 3 CONVERSION 11.1.25 | SDC Columbia | Convergint | Security | 6 | weekly_project_summary.html
2025-11-01 | SDC COL B DATA HALL 1&2 TIER 3 CONVERSION 11.1.25 | SDC Columbia | EATON | UPS/START UP | 2 | weekly_project_summary.html
2025-11-01 | SDC COL B DATA HALL 1&2 TIER 3 CONVERSION 11.1.25 | SDC Columbia | HOLMES | LV/MV | 5 | weekly_project_summary.html
2025-11-01 | SDC COL B DATA HALL 1&2 TIER 3 CONVERSION 11.1.25 | SDC Columbia | KBA | CX | 2 | weekly_project_summary.html
2025-11-01 | SDC COL B DATA HALL 1&2 TIER 3 CONVERSION 11.1.25 | SDC Columbia | McKinstry | HVAC/PIPEFITTERS | 3 | weekly_project_summary.html
2025-11-01 | SDC COL B DATA HALL 1&2 TIER 3 CONVERSION 11.1.25 | SDC Columbia | PCI | DEMO/INSTALL | 4 | weekly_project_summary.html
2025-11-01 | SDC COL B DATA HALL 1&2 TIER 3 CONVERSION 11.1.25 | SDC Columbia | SUNBELT | COMMS | 1 | weekly_project_summary.html
2025-11-01 | SDC COL B DATA HALL 1&2 TIER 3 CONVERSION 11.1.25 | SDC Columbia | Sabey | GC | 5 | weekly_project_summary.html
2025-11-01 | SDC COL B DATA HALL 1&2 TIER 3 CONVERSION 11.1.25 | SDC Columbia | Shield of Armor | Safety | 2 | weekly_project_summary.html
2025-11-01 | SDC Columbia 24 7 051 SDC COL E Shell Core LLO 11 1 2025 | SDC Columbia | C.S I | 3rd party rebar, soils, concrete & welding testing & inspections | 1 | weekly_project_summary.html
2025-11-01 | SDC Columbia 24 7 051 SDC COL E Shell Core LLO 11 1 2025 | SDC Columbia | Coastal Erectors | Structural Steel Erection | 5 | weekly_project_summary.html
2025-11-01 | SDC Columbia 24 7 051 SDC COL E Shell Core LLO 11 1 2025 | SDC Columbia | Complete Design | Survey | 1 | weekly_project_summary.html
2025-11-01 | SDC Columbia 24 7 051 SDC COL E Shell Core LLO 11 1 2025 | SDC Columbia | Flynn Roofing | Roofing | 12 | weekly_project_summary.html
2025-11-01 | SDC Columbia 24 7 051 SDC COL E Shell Core LLO 11 1 2025 | SDC Columbia | Holmes Electric | Electrical | 22 | weekly_project_summary.html
2025-11-01 | SDC Columbia 24 7 051 SDC COL E Shell Core LLO 11 1 2025 | SDC Columbia | McKinstry | HVAC | 4 | weekly_project_summary.html
2025-11-01 | SDC Columbia 24 7 051 SDC COL E Shell Core LLO 11 1 2025 | SDC Columbia | McKinstry | Fitters/Mech | 3 | weekly_project_summary.html
2025-11-01 | SDC Columbia 24 7 051 SDC COL E Shell Core LLO 11 1 2025 | SDC Columbia | McKinstry | Fire Protection | 4 | weekly_project_summary.html
2025-11-01 | SDC Columbia 24 7 051 SDC COL E Shell Core LLO 11 1 2025 | SDC Columbia | McKinstry | Plumbing | 2 | weekly_project_summary.html
2025-11-01 | SDC Columbia 24 7 051 SDC COL E Shell Core LLO 11 1 2025 | SDC Columbia | P.C.I | Framing, Gypsum, Finishes, Gordon Grid, HM door frames | 16 | weekly_project_summary.html
2025-11-01 | SDC Columbia 24 7 051 SDC COL E Shell Core LLO 11 1 2025 | SDC Columbia | Rainier Concrete | Concrete | 6 | weekly_project_summary.html
2025-11-01 | SDC Columbia 24 7 051 SDC COL E Shell Core LLO 11 1 2025 | SDC Columbia | Sabey | GC | 4 | weekly_project_summary.html
2025-11-01 | SDC Columbia 24 7 051 SDC COL E Shell Core LLO 11 1 2025 | SDC Columbia | Skaug Bros Glass | Glazing | 5 | weekly_project_summary.html
2025-11-01 | SDC Columbia 24 7 051 SDC COL E Shell Core LLO 11 1 2025 | SDC Columbia | Tripoint | Civil | 4 | weekly_project_summary.html
2025-11-01 | SDC Columbia 24 7 051 SDC COL E Shell Core LLO 11 1 2025 | SDC Columbia | Uni-Pro | Interior & exterior caulking | 1 | weekly_project_summary.html
2025-11-01 | SDC QUI E1 MWH23 EX2 Fit Out TI 11.1.25 | SDC Quincy | Accelevation | Hack |  | weekly_project_summary.html
2025-11-01 | SDC QUI E1 MWH23 EX2 Fit Out TI 11.1.25 | SDC Quincy | CSI | Inspection | 1 | weekly_project_summary.html
2025-11-01 | SDC QUI E1 MWH23 EX2 Fit Out TI 11.1.25 | SDC Quincy | Convergint | Security | 3 | weekly_project_summary.html
2025-11-01 | SDC QUI E1 MWH23 EX2 Fit Out TI 11.1.25 | SDC Quincy | Holmes Electric | Electrical | 8 | weekly_project_summary.html
2025-11-01 | SDC QUI E1 MWH23 EX2 Fit Out TI 11.1.25 | SDC Quincy | Holmes LV | Low Volt | 4 | weekly_project_summary.html
2025-11-01 | SDC QUI E1 MWH23 EX2 Fit Out TI 11.1.25 | SDC Quincy | Hudson Bay | Insulation/Fireproofing |  | weekly_project_summary.html
2025-11-01 | SDC QUI E1 MWH23 EX2 Fit Out TI 11.1.25 | SDC Quincy | Master Millworks | Cabinets |  | weekly_project_summary.html
2025-11-01 | SDC QUI E1 MWH23 EX2 Fit Out TI 11.1.25 | SDC Quincy | McKinstry | Mechanical |  | weekly_project_summary.html
2025-11-01 | SDC QUI E1 MWH23 EX2 Fit Out TI 11.1.25 | SDC Quincy | McKinstry | Fire |  | weekly_project_summary.html
2025-11-01 | SDC QUI E1 MWH23 EX2 Fit Out TI 11.1.25 | SDC Quincy | McKinstry | Pluming |  | weekly_project_summary.html
2025-11-01 | SDC QUI E1 MWH23 EX2 Fit Out TI 11.1.25 | SDC Quincy | PCI | Carpenters | 3 | weekly_project_summary.html
2025-11-01 | SDC QUI E1 MWH23 EX2 Fit Out TI 11.1.25 | SDC Quincy | QMI Floor | Flooring |  | weekly_project_summary.html
2025-11-01 | SDC QUI E1 MWH23 EX2 Fit Out TI 11.1.25 | SDC Quincy | Sabey | GC | 4 | weekly_project_summary.html
2025-11-01 | SDC QUI E1 MWH23 EX2 Fit Out TI 11.1.25 | SDC Quincy | VNR | Roofing |  | weekly_project_summary.html
2025-11-01 | SDC QUI E1 MWH23 EX2 Fit Out TI 11.1.25 | SDC Quincy | Veca | Security |  | weekly_project_summary.html
2025-11-01 | SDC QUI Juniper Office Storage Conversion 11.1.25 | SDC Quincy | CSI | Special Inspections |  | weekly_project_summary.html
2025-11-01 | SDC QUI Juniper Office Storage Conversion 11.1.25 | SDC Quincy | Convergint | Low Volt |  | weekly_project_summary.html
2025-11-01 | SDC QUI Juniper Office Storage Conversion 11.1.25 | SDC Quincy | DE EI | Window Shades | 2 | weekly_project_summary.html
2025-11-01 | SDC QUI Juniper Office Storage Conversion 11.1.25 | SDC Quincy | Floor Right | Flooring |  | weekly_project_summary.html
2025-11-01 | SDC QUI Juniper Office Storage Conversion 11.1.25 | SDC Quincy | Holmes Electric | Electrical |  | weekly_project_summary.html
2025-11-01 | SDC QUI Juniper Office Storage Conversion 11.1.25 | SDC Quincy | McKinstry | Mechanical |  | weekly_project_summary.html
2025-11-01 | SDC QUI Juniper Office Storage Conversion 11.1.25 | SDC Quincy | Mckinstry | Fire Sprinklers | 2 | weekly_project_summary.html
2025-11-01 | SDC QUI Juniper Office Storage Conversion 11.1.25 | SDC Quincy | PCI | Carpenter |  | weekly_project_summary.html
2025-11-01 | SDC QUI Juniper Office Storage Conversion 11.1.25 | SDC Quincy | PCI | Paint |  | weekly_project_summary.html
2025-11-01 | SDC QUI Juniper Office Storage Conversion 11.1.25 | SDC Quincy | Sabey | GC | 1 | weekly_project_summary.html
2025-11-01 | SDC SEA 53 UPS Replacement 11.1.2025 | SDC Seattle | HECO | Electrical | 2 | weekly_project_summary.html
2025-11-01 | SDC SEA 53 UPS Replacement 11.1.2025 | SDC Seattle | KBA | Commissioning |  | weekly_project_summary.html
2025-11-01 | SDC SEA 53 UPS Replacement 11.1.2025 | SDC Seattle | McKinstry | Controls/ R.I. |  | weekly_project_summary.html
2025-11-01 | SDC SEA 53 UPS Replacement 11.1.2025 | SDC Seattle | Praetorian | Electrical | 3 | weekly_project_summary.html
2025-11-01 | SDC SEA 53 UPS Replacement 11.1.2025 | SDC Seattle | Sabey | GC | 2 | weekly_project_summary.html
2025-11-01 | SDC SEA 53 UPS Replacement 11.1.2025 | SDC Seattle | Sunbelt | Controls |  | weekly_project_summary.html
2025-11-01 | SDC SEA 53 UPS Replacement 11.1.2025 | SDC Seattle | Zavtech | Supply/ Support New UPS's |  | weekly_project_summary.html
2025-11-01 | SDC SEA SDC42 Chiller 11.1.2025 | SDC Seattle | HECO | Electrical |  | weekly_project_summary.html
2025-11-01 | SDC SEA SDC42 Chiller 11.1.2025 | SDC Seattle | KBA | Commissioning |  | weekly_project_summary.html
2025-11-01 | SDC SEA SDC42 Chiller 11.1.2025 | SDC Seattle | McKinstry | Mechanical | 3 | weekly_project_summary.html
2025-11-01 | SDC SEA SDC42 Chiller 11.1.2025 | SDC Seattle | Sabey | GC | 2 | weekly_project_summary.html
2025-11-01 | SDC SEA SDC42 Chiller 11.1.2025 | SDC Seattle | Shield Of Armor | Safety |  | weekly_project_summary.html
2025-11-01 | SDC SEA SDC42 Chiller 11.1.2025 | SDC Seattle | Sunbelt | Controls |  | weekly_project_summary.html
2025-11-01 | SEA Providence Pharmacy HVAC TI 11 01 2025 | SDC Seattle | Barnhart | Crane | 2 | weekly_project_summary.html
2025-11-01 | SEA Providence Pharmacy HVAC TI 11 01 2025 | SDC Seattle | Brand-Safeway | Scaffolding | 2 | weekly_project_summary.html
2025-11-01 | SEA Providence Pharmacy HVAC TI 11 01 2025 | SDC Seattle | C&P Paint | Paint | 1 | weekly_project_summary.html
2025-11-01 | SEA Providence Pharmacy HVAC TI 11 01 2025 | SDC Seattle | DPL | D/F/H Union Labor | 1 | weekly_project_summary.html
2025-11-01 | SEA Providence Pharmacy HVAC TI 11 01 2025 | SDC Seattle | Evergreen power | Electrical | 1 | weekly_project_summary.html
2025-11-01 | SEA Providence Pharmacy HVAC TI 11 01 2025 | SDC Seattle | Expert Drywall | Framing / GWB | 3 | weekly_project_summary.html
2025-11-01 | SEA Providence Pharmacy HVAC TI 11 01 2025 | SDC Seattle | G&W Flooring | Flooring |  | weekly_project_summary.html
2025-11-01 | SEA Providence Pharmacy HVAC TI 11 01 2025 | SDC Seattle | MacDonald Miller | Mechanical | 3 | weekly_project_summary.html
2025-11-01 | SEA Providence Pharmacy HVAC TI 11 01 2025 | SDC Seattle | Sabey | GC | 1 | weekly_project_summary.html
2025-11-01 | SEA Providence Pharmacy HVAC TI 11 01 2025 | SDC Seattle | Snyder Roofing | Roofing | 3 | weekly_project_summary.html
2025-11-01 | SEA Providence Pharmacy HVAC TI 11 01 2025 | SDC Seattle | Sunbelt Controls | Controls | 1 | weekly_project_summary.html
2025-11-01 | SEA Providence Pharmacy HVAC TI 11 01 2025 | SDC Seattle | Suppression Systems | Fire alarm |  | weekly_project_summary.html

## Summary
Metric | Value
Projects | 19
Subcontractor lines | 187
Week Ending Date | 2025-11-01