## Page 1
Weekly Job Status Report
|  |  | Week Ending: |  | 2025-10-25
PROJECT NAME: | ASH-A Site/Shell & Core/Data Halls 1&2 LLO
PROJECT NUMBER: | 24-3-013-asha/24-3-014-asha/24-3-052asha-dh1/24-3-053asha-dh2
ARCHITECT: | Corgan
SABEY PROJECT STAFF | Maria Mosley, Hugo Portillo, JC Mao-Alston, Donnie Fields, Ted Satterthwaite, Max Wright, BJ Braden, Jonny G.
START DATE: | 2024-06-10 | BUDGET: |  |  | 312273746
SCHEDULED COMPLETION: | 2026-07-09 | APPROVED CHANGE ORDERS:
PROJECT % COMPLETE: | 7% | REVISED BUDGET |  |  | 312273746
TENANT LEASES: | TBD | EST. COST AT COMPLETION: |  |  | 309923608
|  | CURRENT PROJECTED (+/-) |  |  | 2350138
SCHEDULE STATUS: | Currently on track for July 2026.
*Budget realignment pending finalized design changes
TEAM
| Company | Craft |  | Trade Workers
| Sabey Construction | Contractor |  | 6
| Independence Ex | Civil |  | 14
| ECS Mid-Atlantic | Inspections |  | 2
| Beltway Paving | Concrete |  | 19
| Dyna | Electric |  | 56
| Southland | Pipe Fitters |  | 13
| Southland | Plumbing |  | 4
| Southland | Sheet Metal |  | 5
| Southland | Sprinkler |  | 8
| Cascade Steel | Mis. Metals |  | 5
| Advanced Caulking | Caulker |  | 6
| Power Solutions | Low Voltage, Thermostats |  | 7
| TECTA | Roofing |  | 9
| PCI | Framer/Drywall |  | 32
| KONE | Elevator |  | 2
| Shockey | Concrete Patching |  | 4
| Highom | Painter |  | 3
| SDC-IGA-Building A | Total people on site |  | 195
WORK PERFORMED:
SCI | Jobsite general cleaning, coordination, supervision, safety/quality control, and offsite parking maintenance, directing on site truck traffic and site logistics. Cleaning floors and putting up plastic over the windows in preparation for winter. Sealing gaps in preparation of the stair landing pour.
Independence Ex | Continuing the reclaimed water to the West. Loading out dirt and grading behind the curb in the west.
ECS Mid-Atlantic | Continue Inspecting compaction for the backfill of ditches. Taking concrete cylinders for the concrete pours. Continue Inspecting roofing of the building. Marking any holes in the vapor barrier for repairs.
Beltway Paving | Finished pouring the slab on grade pads to the West. . Prepped USS pads in the Northeast yard. Poured curb to the West.
DYNA | Running conduit for the in A35 and A23. Installing hanger for the OH conduit rack in A35and A23.Laying out for priority wall penetrations. Working on temp power for the temporary heaters and freight elevator work.
Southland, Pipe Fitters | Installing 12" cold water piping for the second floor core. Leveling CRAHs in A35, doing a punch list and covering with plastic.
Southland Plumbing | Installing water piping on the 3rd and 2nd floor to the East and the Core. Installing roof drain piping through the interior of the core. Setting floor drains in slab on grade West.
Southland Sheet Metal | Installing ductwork in the core, verified penetration locations and sizes. Taking delivery of duct work. Installing DOAS ductwork in A35 and A23. Prepping for the DOAS units on the roof.
Southland Sprinkler | Installing sprinkler lines in the Core, first floor.
Cascade Steel | Building frames for A35 chillers on the ground and craning them to the roof.
Advanced Caulking | Caulking on the inside, outside of the Core and West end of the building. Continue filling control joints in the West with polyurea.
Power Solutions | Installing conduit in a 35 for low voltage to allow for wall close in.
Tecta Roofing | Detailing out the main roof and installing downspouts and wall cap.
PCI | Finish framing up CRAH openings in A35 and framing walls on the first floor core. Beginning on framing the penthouse.
KONE | Continue working on the passenger elevator.
Shockey | Skim coating precast walls that came on site rough and washing the outside of the building in the attempt to color match. Continuing punchout throughout the building.
Higham | Continuing painting the priority walls and the walls behind the CRAHs
Safety meeting, Near Misses: | General site safety. Being safe with man lifts and being aware of what is above you when you are going up.
Upcoming Work
SCI | Jobsite general cleaning, coordination, supervision, safety/quality control, and offsite parking maintenance, directing on site truck traffic and site logistics. Cleaning floors and putting up plastic over the windows in preparation for winter. Barricading temp. propane tanks.
Independence Ex | Testing the reclaimed waterline in the South. Backfilling all of the curb that has been poured to the West. Prepping for future crane picks. Digging for DYNA in the West on security conduits.
ECS Mid-Atlantic | Continue Inspecting compaction for the backfill of ditches. Taking concrete cylinders for the concrete pours. Inspecting roofing for the building.
Beltway Paving | Poured concrete on the 1st floor slab on grade West from 6 to 7 and 8 to 9 line in the West. Pouring the USS pads in the Northeast gen. yard.
Dyna | Digging for security and grounding to the West. Hanging conduit throughout the building. Setting 2 EDCs in A35 gen yard.
Southland, pipe fitters | Installing 12" chilled water piping in the core 3rd floor moving down to install 12" chilled water piping on the second floor. Trimming in CRAHs in A 35. Craning in piping in A23 and setting chillers for A35.
Southland Plumbing | Continue hanging water piping and sanitary in the core.
Southland Sheet Metal | Prepping for DOAS unit install. Installing DOAS units.
Southland Sprinkler | Installing sprinkler pipe in the first floor core.
Advanced Caulking | Continue caulking the wall joints inside and outside to the West. Caulking the inside of the passenger elevator.
Power Solutions | Continue installing conduits for low voltage controls
TECTA Roofing | Start installing wall caps and continue detailing out the roof. Start running the passenger elevator for the other trades to do work inside the shaft.
PCI | Continue framing in the CRAH walls in A23. Continue framing in walls in the core.
KONE | Continue working on the passenger elevator.
Shockey | Continue working on the punchout list. Pouring the West screen wall panels at the plant.
Higham | Painting priority walls in preparation of high work
Prepared by: BJ Braden
Safety meeting, Near Misses: | General site safety. Being safe with man lifts and being aware of what is above you when you are going up.