## Page 1
Weekly Job Status Report
|  |  | Week Ending: |  | 2025-10-25
PROJECT: | ASH-AB1-1 3 MW Fit Out TI
PROJECT NUMBER: | 25-5-125
ARCHITECT: | Sabey
SABEY PROJECT STAFF | Maria Mosley,Mahad Mohamed, Hugo Portillo,Ted Satterthwaite
START DATE: | 2025-09-02 | BUDGET: |  |  | 5999535
SCHEDULED COMPLETION: | 2025-12-01 | APPROVED CHANGE ORDERS:
PROJECT % COMPLETE: | 98% | REVISED BUDGET |  |  | 5999535
TENANT LEASES: | Oracle | EST. COST AT COMPLETION: |  |  | 7422417
|  | CURRENT PROJECTED (+/-) |  |  | -1422882
*Post lease execution scope changes [sub-let cage] and acceleration [6 weeks] request by Tenant. Lease service order pending to increase budget.
TEAM
| Company | Craft |  | Trade Workers
| Sabey Construction | GC |  | 2
| CPG | TI GC |  | 4
| NOVA | Electrical |  | 9
| CCCI | Low Voltage |  | 5
WORK PERFORMED:
SCI | Cleaning and supervision
CPG | Supervision
NOVA | Clean up and punch list items
CCCI | Pulling fiber, testing and terminating fiber
Safety Meeting: | Lock Out Tag Out
UPCOMING WORK:
SCI | Cleaning and supervision
CPG | Supervision
NOVA | Clean up and punch list
CCCI | Terminating fiber
Safety Meeting: | Lock Out Tag Out
Prepared By: BJ Braden