## Page 1
Weekly Job Status Report
|  |  | Week Ending: |  | 2025-10-25
PROJECT NAME: | SDC AUS-Building B + DH's B35 - B36
PROJECT NUMBER: | 25-4-085 & 25-4-086 & 25-4-087 & 25-4-088
ARCHITECT: | Corgan
SABEY PROJECT STAFF | Jeff Giguiere, Gabe Encarnacion, Sara Bigon, Don Fields, Barry Hunter, Peter Mar
START DATE: | 2025-03-24 | BUDGET: |  |  | 307442294
SCHEDULED COMPLETION: | 2028-03-05 | APPROVED CHANGE ORDERS:
PROJECT % COMPLETE: | 4.99% | REVISED BUDGET |  |  | 307442294
TENANT: | TBD | EST. COST AT COMPLETION: |  |  | 307442294
|  | CURRENT PROJECTED (+/-) |  |  | 0
SCHEDULE STATUS: | ON SCHEDULE -
TEAM
| Company | Craft |  | Trade Workers
| Sabey | GC |  | 1
| Mckinstry - McK | Mechanical
| Kent | Concrete |  | 23
| Tindall | Precast |  | 8
| TBD | Fireproofing
| AO Services | Trenching |  | 5
| Big State Electric - BSE | Electrical |  | 6
| PCI | Framing / GWB
| CMP | Steel
| Medel | Taping / Painting
| Chasco | Grading |  | 14
| TBD | D/F/H
| ECS | Special Inspections
| McKinstry - McK | Fire Sprinklers
| Seimens | Fire Detection
WORK PERFORMED:
Sabey | Site safety, coordination
Mechanical - Mck
Electrical - BSE | UG electrical vault excavation and installation with backfil.
Grading | Excavation of Yard C and haul off spoils
Wet Utilities | Installation of 42" RCP line A.
Trenching | Trenching for UG utilities (tele-com)
Precast | Crane set up for start of precast
Structural Steel - CMP
Taping / Painting
HTI
Concrete | Drilling of piers. Grade beam excavation. Concrete pouring of grade beams and piers. Rebar tieing for grade beams.
AAR Testing
Viking
Supression Systems
SAFETY / NEAR MISSES:
None to report
UPCOMING WORK:
Precast scope of work start.
Prepared By: Peter Mar

## Sheet1
WORK PERFORMED: