## Page 1
Weekly Job Status Report
|  |  | Week Ending: |  | 2025-10-25
PROJECT NAME: | SDC AUS-A11 9MW Data Hall Build Out
PROJECT NUMBER: | 24-4-022 / 24-8-022
ARCHITECT: | Corgan
SABEY PROJECT STAFF | Alfred Ngang, Golden Eke, Jon Hunter, Sara Bigon, Don Fields, Peter Mar
START DATE: | 2024-10-28 | BUDGET: |  |  | 85612098
SCHEDULED COMPLETION: | 2026-02-25 | APPROVED CHANGE ORDERS:
PROJECT % COMPLETE: | 77.1% | REVISED BUDGET |  |  | 85612098
TENANT: | Jane Street | EST. COST AT COMPLETION: |  |  | 87222463
|  | CURRENT PROJECTED (+/-) |  |  | -1610365
SCHEDULE STATUS: | ON SCHEDULE -
*Includes some JS sub costs. Move to JS Fit Out job once approved.
TEAM
| Company | Craft |  | Trade Workers
| Sabey | GC |  | 4
| Mckinstry - McK | Mechanical |  | 9
| PCI | Strut Grid / ACT
| Mckinstry - McK | Demo
| TBD | Fireproofing
| Prestige | Flooring |  | 8
| Big State Electric - BSE | Electrical |  | 42
| PCI | Framing / GWB
| Medel | Drywall Finish/Paint
| Tindall | Precast
| Chasco | Concrete Restoration
| TBD | D/F/H
| SWMCO | Specialty Sub
| PCI | Doors
| QES | EDCs |  | 4
| McKinstry - McK | Fire Sprinklers
| Seimens | Fire Detection
WORK PERFORMED:
Sabey | General trash clean up and sweeping. Moving material and equipment to facilitate work in progress. Clean and wipe down of EDCs in Yard C.
Mechanical - Mck | Prestart up and Cx repairs. Dam install in mech gallery. Tie in sealing of dog-houses on the roof for CHWP.
Electrical - BSE | OH conduit install and conduit down to electrical gear on the east side. Wire pulling during evening shift and conduit install in electrial mechanical room. Cable bus wire pull in Yard C.
Chasco
Paint
Celing
Drywall
Doors
Roofing
SWMCO
EDCs | Repairs on EDCs. ABB working on UPS units in EDCs.
AAR Testing
Raised Floor
Supression Systems - McK
SAFETY / NEAR MISSES:
None to report
UPCOMING WORK:
L3 Start Ups on Electrical Gear
Prepared By: Peter Mar

## Sheet1
WORK PERFORMED: