## Page 1
Weekly Job Status Report
|  |  | Week Ending: |  | 2025-10-25
PROJECT NAME: | SDC Aus TACC 15MW
PROJECT NUMBER: | 24-4-055 A12 / 24-5-058 TI
ARCHITECT: | Corgan
SABEY PROJECT STAFF | Alfred Ngang, Kimberly Rachow, Jon Hunter, Sara Bigon, Don Fields, Peter Mar
START DATE: | 2024-10-28 | BUDGET: |  |  | 55217782
SCHEDULED COMPLETION: | 2026-01-30 | APPROVED CHANGE ORDERS:
PROJECT % COMPLETE: | 74.8% | REVISED BUDGET |  |  | 55217782
TENANT: | UT Adv Compute Ctr | EST. COST AT COMPLETION: |  |  | 55217268
|  | CURRENT PROJECTED (+/-) |  |  | 514
SCHEDULE STATUS: | ON SCHEDULE -
TEAM
| Company | Craft |  | Trade Workers
| Sabey | GC |  | 1
| Mckinstry - McK | Mechanical |  | 8
| PCI | Strut Grid / ACT
| Medel | Paint
| TBD | Fireproofing
| TBD | Low Volt
| Big State Electric - BSE | Electrical |  | 16
| PCI | Framing / GWB |  | 4
| Ventana | Glazing
| Prestige | Flooring |  | 4
| Chasco | Concrete
| TBD | D/F/H
| ECS | Special Inspections
| McKinstry - McK | Fire Sprinklers |  | 2
| Seimens | Fire Detection
WORK PERFORMED:
Sabey | General clean up and sweeping of space, checking of dehumidifiers.
Mechanical - Mck | CHWP install of the Technology loop.
Electrical - BSE | Wire pulling for switchgear. Chiller wire terminations on roof. Underground conduit in Yard F for metering on MVS.
Concrete
Medel
Prestige - Flooring | Install ramp up to white space from shell space.
Drywall | Drywall patching for CHWP.
Structural Steel - CMP
Roofing
HTI
Structural Ceiling
AAR Testing
Glazing
Supression Systems | VESDA system installation
SAFETY / NEAR MISSES:
none to report
UPCOMING WORK:
Prepared By: Peter Mar

## Sheet1
WORK PERFORMED: