## Page 1
Weekly Job Status Report
|  |  | Week Ending: |  | 2025-10-25
PROJECT NAME: | SDC 43 6 MW Data Hall
PROJECT NUMBER: | 23-7-719 / DEV 23-8-719
ARCHITECT: | Sabey Architect
SABEY PROJECT STAFF | James Conley / Glenn Parry / Sergio Ortega
START DATE: | 2024-09-03 | BUDGET: |  |  | 65717733
SCHEDULED COMPLETION: | 2025-12-12 | APPROVED CHANGE ORDERS: |  |  | 0
PROJECT % COMPLETE: | 92% | REVISED BUDGET |  |  | 65717733
TENANT: | Akamai | EST. COST AT COMPLETION: |  |  | 63153051
|  | CURRENT PROJECTED (+/-) |  |  | 2564682
SCHEDULE STATUS: | ON SCHEDULE -
TEAM
| Company | Craft |  | Trade Workers
| Sabey | GC |  | 2
| Mckinstry | Mechanical |  | 14
| Tbar | Strut Grid / ACT |  | 0
| WPI | Paint / Raised Floor |  | 0
| Glumac | CX |  | 0
| Holmes LV | Low Volt |  | 0
| Holmes Electric | Electrical |  | 12
| Expert Drywall | Framing / GWB |  | 1
| Praetorian | Electrical Testing |  | 1
| Snyder Roofing | Roofing |  | 0
| Cochran | Cameras/Security |  | 1
| Barclay Dean | D/F/H |  | 2
| NC / CAT | Generators |  | 2
| Viking | Fire Sprinklers |  | 0
| Supression Systems | Fire Detection |  | 0
WORK PERFORMED:
Sabey | clean up, dump trash, daily site walks and sub coordination, Cx Alloy L3 checklists, set up rental load banks on 3rd floor
Mckinstry | day tank fuel piping testing, clean up, and labeling, fuel system controler RI and wiring pulling, Cx Alloy checklists, Diaken onsite for Sycool startup activities, sunbelt working on integration w/ daiken, loadbank testing with Munters Sycool
Tbar
WPI
Glumac
HECO | finish up lighting on 1st floor, start labeling and phenolics, assist with Mitsu UPS startup, prep CDPs for load banking, clean up Gen room temp power and lighting, IEM onsite for 2 warrenty repairs
Expert Drywall | building pods for load banking
Praetorian Power | Cx alloy test report uploading, ATS-B CT retest
Synder Roofing
Cochran
Barclay Dean
NC / CAT | Working on GEN-A comm upgrade and ground fault, install batteries and wiring
Viking
Supression Systems
SAFETY / NEAR MISSES:
no incidents, weekly safety topic - LOTO, who can operate breakers.
UPCOMING WORK:
Cx, load bank use, L4s
Prepared By: James Conley

## Sheet1
WORK PERFORMED: