## Page 1
Weekly Job Status Report
|  |  | Week Ending: |  | 2025-10-25
PROJECT NAME: | IGQ-QUI-E1 9MW Data Hall LLO.
PROJECT NUMBER: | 24-7-031
ARCHITECT: | Sabey Architecture, Corgan
SABEY PROJECT STAFF | Connie Taylor, Max Wright, Aaron Sepanski, Kevin Bunde, Gilbert Tudesque, Lacey plumage, Tammy Gonzales.
START DATE: | 2024-08-21 | BUDGET: |  |  | 88368880
SCHEDULED COMPLETION: | 2025-11-01 | APPROVED CHANGE ORDERS: |  |  | 0
PROJECT % COMPLETE: | 99% | REVISED BUDGET |  |  | 88368880
TENANT | Microsoft | EST. COST AT COMPLETION: |  |  | 88966949
|  | CURRENT PROJECTED (+/-) |  |  | -598069
SCHEDULE STATUS: | ON SCHEDULE -
*Over-run due to: switch Zinc batteries to VRLA, CX Mgr, Safety, Security, Plumbing, Insepctions.
TEAM
| Company | Craft |  | Trade Workers
| Sabey | GC |  | 4
| McKinstry | Mechanical |  | 0
| McKinstry | Fire Protection |  | 0
| McKinstry | Sheet Metal |  | 1
| McKinstry | Mechanical Cx |  | 5
| PCI | Carpentry |  | 2
| Holmes Electric | Electrical |  | 13
| Tripoint | Civil |  | 0
| Shield of Armor | Safety |  | 2
| Praetorian | NETA Testing |  | 2
| NC Power | Generator Tech |  | 2
| All Valley Sheet Metal | Sheet Metal |  | 0
| Hudson Bay | Insulator |  | 0
| IEM | IE Vendor |  | 3
| IE | EDC |  | 1
| MEPPI | HVAC |  | 1
| Zavtek | PDU Vendor |  | 1
| C&C Power | Battery Vendor |  | 1
| ABB | UPS Vendor |  | 1
| KBA | Cx Agent |  | 3
| Clean Sweep | Landscape |  | 2
WORK PERFORMED:
Sabey | Supervision, Scheduling, site services, MOP reviews, QA/QC. Cleaning electrical yard, removing materials out of it. Unload equipment. Completed pressure washing the CMU wall. Removed temp power skid protection. Installed covers at LB penetrations in the Kingspan. Finished up misc. wall base install and fire caulking. Cleaned out data halls for IST. Performed fire watch during IST in data halls A&B. Removed rental load banks and fan carts from data halls A&B post IST. Rolled up rental SO cords and prep for shipping.
McKinstry Mechanical | No work.
McKinstry Fire Protection | No work.
McKinstry Sheet Metal | Caulked wall angle base in the East gallery.
McKinstry Cx | Completed TAB for the added transfer fan for the MMR. Supported electrical Cx with cooling on the floor. IST data halls A&B.
Holmes Electric | Installed PT cabinet for the MV cutover, tested, landed cables tying QE1 to QE2. Installed ARC flash stickers. Performed IR scans. Fire caulked MMR. Added lugs in HDP boards for future load bank provisions. Programmed lighting controls. Rewired horn strobes in the EDC's. IST for QE1-A&B (lineups R, A, B & C). finalized panel schedules. Removed whips from PDU's, post IST of data halls A&B. Assisted with rolling up load banks cables. L4 tested EDC-F. Hooked load banks back to try burn the off gassing in the EDC's.
PCI | Completed trade damage touchups in data hall C and moved into data hall D. Touched up doors and frames throughout.
Tri-Point | No work.
Shield of Armor | Site safety meeting, site walks and safety audits, new hire orientations. Manage LOTO operations.
Praetorian | Tested cables for the MV cutover.
All Valley Sheet metal | No work.
Hudson Bay | No work.
NC Power | Supported Cx/IST activities.
IEM | Supported Cx/IST activities.
IE | No work.
MEPPI | Supported IST.
Zavtek | Supported IST. Worked through STS/PDU issues.
C&C Power | Supported IST.
ABB | Continued working UPS-F issues. Supported Cx/IST activities.
KBA | L4 tested EDC-F. IST data halls A&B? and LLO security.
Clean Sweep | Completed landscaping South of the chiller yard.
SAFETY / NEAR MISSES:
This weeks safety: Hydration
DELAYS:
UPCOMING WORK:
Punch list items. IST of data halls C&D.
Prepared By:
Kevin Bunde

## Sheet1
WORK PERFORMED: