## Page 1
Weekly Job Status Report
|  |  | Week Ending: |  | 2025-10-25
PROJECT NAME: | IGQ-QUI-E6 ZOHO OFFICE EXPANSION LLO
PROJECT NUMBER: | 25-7-131
ARCHITECT: | Sabey Architecture.
SABEY PROJECT STAFF | Connie Taylor, Lacey Plumage, Kevin Bunde, Gilbert Tudesque
START DATE: | 2025-09-22 | BUDGET: |  |  | 81046
SCHEDULED COMPLETION: | 2025-10-30 | APPROVED CHANGE ORDERS: |  |  | 0
PROJECT % COMPLETE: | 98% | REVISED BUDGET |  |  | 81046
TENANT | ZOHO | EST. COST AT COMPLETION:
|  | CURRENT PROJECTED (+/-) |  |  | 81046
SCHEDULE STATUS: | ON SCHEDULE -
TEAM
| Company | Craft |  | Trade Workers
| Sabey | GC |  | 2
| Hudson Bay | Insulator |  | 1
| McKinstry | Sheet Metal |  | 0
| PCI | Carpentry |  | 2
| Holmes Electric | Electrical |  | 0
WORK PERFORMED:
Sabey | Supervision, Scheduling, MOP reviews, QA/QC. General cleaning.
Hudson Bay | Insulated the extended ducting.
McKinstry Sheet Metal | No Work
McKinstry Cx | No Work
Holmes Electric | No Work
PCI | Completed grid and dropped ceiling tiles.
SAFETY / NEAR MISSES:
None to report
UPCOMING WORK:
Carpet and Base.
Prepared By:
Kevin Bunde

## Sheet1
WORK PERFORMED: