## Page 1
Weekly Job Status Report
|  |  | Week Ending: |  | 2025-10-25
PROJECT NAME: | James Tower Elevator Modernization
PROJECT NUMBER: | 24-2-034 DEV 24-8-034
ARCHITECT: | Sabey Architect
SABEY PROJECT STAFF | Rob Pritchett/ Charles Fair
START DATE: | 2024-09-09 | BUDGET: |  |  | 1722561
SCHEDULED COMPLETION: | 2025-11-27 | APPROVED CHANGE ORDERS: |  |  | 0
PROJECT % COMPLETE: | 42% | REVISED BUDGET |  |  | 1722561
TENANT | N/A | EST. COST AT COMPLETION: |  |  | 1717394
|  | CURRENT PROJECTED (+/-) |  |  | 5167
SCHEDULE STATUS: | BEHIND SCHEDULE - Scheduled completion changed from 10-10-25 To 11-7-25 Due to structural beam repairs and RED TAG. / 1-7-2025 -It now looks like we are 1 month behind most current updated schedule. / 1-17-2025 - New updated schedule has a completion date of 11-27-2025.
TEAM
| Company | Craft |  | Trade Workers
| Sabey | GC |  | 1
| Otis Elevator | Elevator Modernization |  | 2
| 16DLLC | Custom Elevator Fabrication |  | 2
| Chinook | Elevator Interior |  | 0
WORK PERFORMED:
Troubleshooting and final inspection on elevator car 2.
UPCOMING WORK:
Running elevator 2 up and down and trouble the elevator car for two weeks. Then we can turn the elevator over to public.
SAFETY/NEAR MISSES | None to report