## Page 1
Weekly Job Status Report
|  |  | Week Ending: |  | 2025-10-25
PROJECT NAME: | Jefferson Garage Elevator Modernization
PROJECT NUMBER: | 24-2-033 DEV 24-8-033
ARCHITECT: | Sabey Architect
SABEY PROJECT STAFF | Rob Pritchett, Matt Meile Charlie Fair
START DATE: | 2024-09-09 | BUDGET: |  |  | 1301574
SCHEDULED COMPLETION: | 2026-01-12 | APPROVED CHANGE ORDERS: |  |  | 0
PROJECT % COMPLETE: | 69% | REVISED BUDGET |  |  | 1301574
TENANT | N/A | EST. COST AT COMPLETION: |  |  | 1253019
|  | CURRENT PROJECTED (+/-) |  |  | 48555
SCHEDULE STATUS: | ON SCHEDULE - 2 Cars in the public Garage are 100% Complete. 2 cars in the reserve garage are set to start 7-14-2025
CONTRACT STATUS | MER approved 5/10/24
TEAM
| Company | Craft |  | Trade Workers
| Sabey | GC |  | 1
| Otis Elevator | Elevator Modernization |  | 2
| Chinook Elevator | Elevator Interiors |  | 0
| Todd Folden | Elevator consultant |  | 0
| West Coast Flooring | Carpet installers |  | 0
| D 16 | elevator inspection |  | 2
WORK PERFORMED:
Wiring and troubleshooting elevator car. Final inpection on elevator car.
Troubleshot all Components to get finalizing the elevator.
SAFETY/NEAR MISSES: Clean work areas. Making sure that there is at least two workers working on elevator at all time.