## Page 1
Weekly Job Status Report
|  |  | Week Ending: |  | 2025-10-25
PROJECT NAME: | SDC-QUI-E1-MWH23-EX2 TI
PROJECT NUMBER: | 24-5-072, 24-5-073, 24-5-075, 24-5-076, 25-5-092, 25-5-093, 25-5-097, 25-5-099, 25-5-100, 25-5-101, 25-5-102, 25-5-114, 25-5-115, 25-5-119
Design Team: | Corgan, WB, Introva
SABEY PROJECT STAFF | Connie Taylor, Tammy Gonzales, Lacey Plumage, Gilbert Tudesque, Kevin Bunde
START DATE: | 2025-03-10 | BUDGET: |  |  | 8305549
SCHEDULED COMPLETION: | 2025-11-01 | APPROVED CHANGE ORDERS:
PROJECT % COMPLETE: | 96% | REVISED BUDGET |  |  | 8305549
Tenant | Microsoft | EST. COST AT COMPLETION: |  |  | 8304597
|  | CURRENT PROJECTED (+/-) |  |  | 952
SCHEDULE STATUS: | ON SCHEDULE -
TEAM
| Company | Craft |  | Trade Workers
| Sabey | GC |  | 4
| McKinstry | Mechanical |  | 0
| McKinstry | Fire |  | 0 | 1
| McKinstry | Pluming |  | 0 | 2
| VNR | Roofing | Pluming | 0
| PCI | Carpenters |  | 3
| Hudson Bay | Insulation/Fireproofing |  | 0
| Holmes LV | Low Volt |  | 4
| Holmes Electric | Electrical |  | 8
| Accelevation | Hack |  | 0
| Master Millworks | Cabinets |  | 0
| QMI Floor | Flooring |  | 0
| Convergint | Security |  | 3
| Veca | Security |  | 0
| CSI | Inspection |  | 1
WORK PERFORMED:
Sabey | General cleaning . Unloading trucks and demobilize. Finish Anchoring down racks in room 218 and 217 for client. Place corner Guards in breaker room.
McKinstry Fire | No work this week.
McKinstry Pluming | No work this week.
PCI | Punch list item in 219 and 218B. Replace damage tiles. Painted 2ND coat in Telco closet.
Hudson Bay | No work this week.
Holmes LV | Working on down spouts and testing fiber from SCCR racks to IDF room. Install exterior cameras in gen yard and chiller yard. Finish pulling security fiber for exterior doors in CMU wall and EDC,s.
Holmes Electric | Worked on punch list items and fire caulking through out building. Worked on grounding and bonding rerouting for the TI in QE1-A,B,C. Demobilizing TI job and LLO job and cleaning up. Working on RI report.
Accelevation | No work this week.
CSI | Inspected tenant storage racks for anchor bolts.
VECA | No work this week.
QMI Flooring
Convergint | Working on SCCR and CCR cabinets terminations. |  | inQE1-C and D. Adjusting cameras in QE1-A, Working on security on doors 219 and 204A.
SAFETY / NEAR MISSES:
Do to gassing in EDC,s security commissioning has stopped tell air samples are taken.
UPCOMING WORK:
UPCOMING WORK:
Finish working on completing punch list items and Security commissioning.
Prepared By:
Gilbert Tudesque

## Sheet1
WORK PERFORMED: