## Page 1
Weekly Job Status Report
|  |  | Week Ending: |  | 2025-10-25
PROJECT NAME: | SDC Manhattan: Cooling Tower 6 Study
PROJECT NUMBER: | 25-6-105/25-8-105
ARCHITECT/ENGINEER | Ramboll
SABEY PROJECT STAFF | Lou Vigorito, Ron Cosoleto
START DATE: | 2025-05-06 | BUDGET: |  |  | 190481
SCHEDULED COMPLETION: |  | APPROVED CHANGE ORDERS:
PROJECT % COMPLETE: | 5% | REVISED BUDGET |  |  | 190481
Tenant Leases | N/A | EST. COST AT COMPLETION: |  |  | 190481
|  | CURRENT PROJECTED (+/-) |  |  | 0
SCHEDULE STATUS: | Meetings/Surveys held with Ramboll to discuss options for 6th tower position. Study on hold until balancing of condenser water is completed.
TEAM
| Company | Craft |  | Trade Workers
Ramboll
WORK PERFORMED:
Viking
SAFETY / NEAR MISSES:
N/A
UPCOMING WORK:
Prepared By: Ron Cosoleto

## Sheet1
WORK PERFORMED: