## Page 1
Weekly Job Status Report
|  |  | Week Ending: |  | 2025-10-25
PROJECT NAME: | SDC Manhattan: Local Law 11 Façade Remediation
PROJECT NUMBER: | 24-6-006/24-8-006
ARCHITECT: | Diaz
SABEY PROJECT STAFF | Lou Vigorito, Ron Cosoleto, Willie Rosario
START DATE: | 2024-07-06 | BUDGET: |  |  | 2370285
SCHEDULED COMPLETION: | 2025-08-31 | APPROVED CHANGE ORDERS:
PROJECT % COMPLETE: | 100% | REVISED BUDGET |  |  | 2370285
Tenant Leases | N/A | EST. COST AT COMPLETION: |  |  | 2388602
|  | CURRENT PROJECTED (+/-) |  |  | -18317
SCHEDULE STATUS: | East side scaffolding removed and plaza reopened for public use. Last panel installed on 9/5. Scaffolding fully removed. Closeout documents and permits ongoing. Closeouts completed and handed over to building management.
*Window Wall Legal Fees not budgeted. Offset with contingency
TEAM
| Company | Craft |  | Trade Workers
| Viking | Removal of equipment |  | 0
| Platinum Scaffolding | Removal of sidewalk shed |  | 0
WORK PERFORMED:
Viking
SAFETY / NEAR MISSES:
None to report
UPCOMING WORK:
Prepared By: Ron Cosoleto

## Sheet1
WORK PERFORMED: