## Page 1
Weekly Job Status Report
|  |  | Week Ending: |  | 2025-10-25
PROJECT NAME: | SDC-COL-E Site LLO, Shell & Core, E2 9MW Data Hall Build
PROJECT NUMBER: | 24-7-050-colesi, 24-7-051-colesc, 24-7-023-cole1
DESIGN TEAM: | JHET, DEA, SABEY ARCHITECTURE, McKinstry, ENW,& WB.
4
SABEY PROJECT STAFF: | Max Jones, Fred Deskin, JR Chambers, Patti Guay, Juan Peralta, Clayton Holzerland Aaron Sepanski Michael Throneberry, Cassie Fabian
START DATE: | 2025-02-10 | BUDGET: |  |  | 145037759
SCHEDULED COMPLETION: | 2026-11-01 | APPROVED CHANGE ORDERS: |  |  | 0
PROJECT % COMPLETE: | 42% | REVISED BUDGET |  |  | 145037759
TENANT: | N/A | EST. COST AT COMPLETION: |  |  | 144398226
|  | CURRENT PROJECTED (+/-) |  |  | 639533
SCHEDULE STATUS: | On schedule
TEAM: | Company | Craft |  | Trade Workers
| Sabey | GC |  | 4
| Tripoint | Civil |  | 7
| Complete Design | Survey |  | 1
| Holmes Electric | Electrical |  | 22
| Rainier Concrete | Concrete |  | 0
| C.S I | 3rd party rebar, soils, concrete & welding testing & inspections |  | 0
| P.C.I | Framing, Gypsum, Finishes, Gordon Grid, HM door frames |  | 18
| Flynn Roofing | Roofing |  | 15
| Skaug Bros Glass | Glazing |  | 3
| McKinstry | HVAC |  | 4
| McKinstry | Fitters/Mech |  | 3
| McKinstry | Fire Protection |  | 5
| McKinstry | Plumbing |  | 2
| Coastal Erectors | Structural Steel Erection |  | 0
| Uni-Pro | Interior & exterior caulking |  | 2
| Over Head Door | O.H door furnish & install |  | 3
| Shield of Armor | Jobsite Safety overview |  | 1
| Total number of workers |  |  | 90
WORK PERFORMED:
Sabey | Contractor safety & coordination, asset & risk management, general conditions, QAQC overview, filled scope gaps, prep for supplemental winter heating for CE2 & Core
Tripoint | Finish asphalt gravel top course grade, backfill behind curbs, set 2 eco-block for equipment access into building, graded equipment yard to sub-grade, raised valve cans in roadway.
Complete Design/survey | Set control for front canopy and loading dock.
Holmes Electric | Worked on MV conduits at CE1 equipment yard & Pangborn substation conduit pathway & place RHO concrete, rough in at electrical rooms and AHU roof penetrations & place underground conduits from PME's to USS's at CE2 yard
Rainier Concrete | No work this week
C.S.I | No work this week
PCI | Interior framing, framing at stairwell/penthouse, taping and painting at building Core critical infrastructure areas.
Flynn Roofing | Load materials and place vapor barrior CE1 roof, completed membrane around CE1 chiller platform areas
Coastal Erectors | No work this week
Skaug Bros Glass | Set window frames at west pre-cast panel wall opening
McKinstry HVAC | Assemble knock down ducts for transfer fan connections
McKinstry Fitter | Installing chilled water piping in east CRAH gallery
McKinstry Fire | Continued Installation of main and branch line sprinkler piping.
McKinstry Plumbing | Installing hangers & pipe in core areas and CE1.
UNI-PRO | Continued Precast wall joint caulking.
Overhead Door | Set O.H coiling doors at loading dock
Shield of Armor Safety | Conducted all hand weekly meeting, participates in daily foreman logistics meeting, reviews and file sub safety narratives.
SAFETY / NEAR MISSES:
Daily equipment checklist has a few contractor deficiencies we will address at our upcoming ALL hands weekly safety discussion.
UPCOMING WORK: Place layer #1of 2 asphalt pavement at north, south and west roadways this year, continued roofing , framing, fire protection, electrical lighting and electrical room rough in, HVAC duct drop installation, chiller piping, prep to mobilize CRAH unit into building, branch line water piping, hangers and roof drains at Core and connection to storm line, FRP entry concrete for canopy erection, excavate for loading dock footing and stemwall, set CE1 chiller supports, place conduit and RHO concrete at CE! yard and MV pathway to Pangborn sub-station, caulking of interior precast concrete panel joint, install glazing at exterior, continue CE1 vapor barrio and membrane installation
Prepared By:
Fred Deskin

## Sheet1
WORK PERFORMED: