## Page 1
Weekly Job Status Report
|  |  | Week Ending: |  | 2025-10-25
PROJECT NAME: | SDC-COL-B DATA HALL 1&2 TIER 3 CONVERSION
PROJECT NUMBER: | 24-7-079
Architect | Sabey Architecture
SABEY PROJECT STAFF | Max Jones, Juan Peralta, Patti Guay,Michael Throneberry.
START DATE: | 2025-03-24 | BUDGET: |  |  | 14899616
SCHEDULED COMPLETION: | 2025-12-01 | APPROVED CHANGE ORDERS:
PROJECT % COMPLETE: | 96% | REVISED BUDGET |  |  | 14899616
TENANT | Crowdstrike/VULTR | EST. COST AT COMPLETION: |  |  | 14721079
|  | CURRENT PROJECTED (+/-) |  |  | 178537
SCHEDULE STATUS: | On Schedule
TEAM
| Company | Craft |  | Trade Workers
| Sabey | GC |  | 5
| HOLMES | LV/MV |  | 14
| McKinstry | HVAC/PIPEFITTERS |  | 0
| PCI | DEMO/INSTALL |  | 2
| Accelevation | Demo |  | 0
| Shield of Armor | Safety |  | 1
| Convergint | Security |  | 1
| CBS | Maintenance Testing |  | 0
| EATON | UPS/START UP |  | 2
| SUNBELT | COMMS |  | 1
WORK PERFORMED:
SABEY | CONTINUED CB2 DEMO OF EXISTING HAC'S, CLEANED UP CB3 BEHIND HOLMES,
HOLMES | RPP Whips complete minus the 2 missing whips. Terminations on HDP side for gen complete. Gen side 50%. Clean up and de-mobilization. SKRU wiring completed on CB3-A, C, Need to install and hook up a few more control wires on R and B.
Accelevation
SHEILD OF ARMOR | SAFETY WALK THROUGH, SAFETY AUDIT
Convergint
EATON | FINISHED UP UPS START UP C-LINE CB3
MCKINSTRY
CONVERGINT | SECURITY CROSSOVER TROUBLESHOOTING
CBS
SUNBELT | UPS COMM WORK AND TROUBLESHOOTING
PCI | CONTINUED T-BAR REPAIR AND CEILING TILE INSTALL
SAFETY / NEAR MISSES:
NO INJURIES REPORTED, TALKED ABOUT FIRST AID USAGE OF SDC'S MATERIAL
UPCOMING WORK:
CX TO START IN CB3 10/28/25, CONTINUED CB2 DEMO
Prepared By: Michael Throneberry

## Sheet1
WORK PERFORMED: