## Page 1
Weekly Job Status Report
|  |  | Week Ending: |  | 2025-10-25
PROJECT NAME: | SDC-QUI-C Juniper Office-Storage Conversion
PROJECT NUMBER: | 25-7-132
ARCHITECT: | Brandon Harris
SABEY PROJECT STAFF | Connie,Kevin,Gilbert,Lacey.
START DATE: | 2025-09-22 | BUDGET: |  |  | 428230
SCHEDULED COMPLETION: | 2025-12-12 | APPROVED CHANGE ORDERS: |  |  | 0
PROJECT % COMPLETE: | 20% | REVISED BUDGET |  |  | 428230
|  | EST. COST AT COMPLETION: |  |  | 428230
Tenant: | Juniper | CURRENT PROJECTED (+/-) |  |  | 0
SCHEDULE STATUS: | ON SCHEDULE -
TEAM
| Company | Craft |  | Trade Workers
| Sabey | GC |  | 1
| McKinstry | Mechanical |  | 0
| PCI | Carpenter |  | 0
| PCI | Paint |  | 0
| Convergint | Low Volt |  | 0
| Holmes Electric | Electrical |  | 0
| Floor Right | Flooring |  | 0
| CSI | Special Inspections |  | 0
| Mckinstry | Fire Sprinklers |  | 1
| DE EI | Window Shades |  | 2
WORK PERFORMED:
Sabey | Supervision. Scheduling. Helped unload sprinkler pipe and stock into storage room.
McKinstry | Unload sprinkler pipe.
PCI
Convergint
Floor Right | Waiting on delivery of ESD flooring.
HECO | No work this week.
HECO LV. | Waiting on changes to LANEL system design to proceed.
City of Quincy
DE EI | no work this week.
SAFETY / NEAR MISSES:
None to report
UPCOMING WORK:
Up sizing all sprinkler mains for new sprinkler system, Start demo existing sprinkler system Monday.
Prepared By: Gilbert Tudesque

## Sheet1
WORK PERFORMED: