## Page 1
Weekly Job Status Report
|  |  | Week Ending: |  | 2025-10-25
PROJECT NAME: | SDC-SEA-53 UPS Replacement:
PROJECT NUMBER: | 24-7-077
ARCHITECT: | Sabey Architecture:
SABEY PROJECT STAFF: | Glenn Parry, Matt Meile
START DATE: | 2025-06-24 | BUDGET: |  |  | 2574562
SCHEDULED COMPLETION: | 2025-11-04 | APPROVED CHANGE ORDERS:
PROJECT % COMPLETE: | 96% | REVISED BUDGET |  |  | 2574562
TENANT: | N/A | EST. COST AT COMPLETION: |  |  | 2574562
|  | CURRENT PROJECTED (+/-) |  |  | 0
SCHEDULE STATUS: | ON SCHEDULE -
TEAM:
| Company | Craft |  | Trade Workers
| Sabey | GC |  | 2
| HECO | Electrical |  | 1
| Zavtech | Supply/ Support New UPS's |  | 2
| Sunbelt | Controls |  | 1
| McKinstry | Controls/ R.I. |  | 2
| KBA | Commissioning |  | 1
| Praetorian | Electrical |  | 0
WORK PERFORMED:
Sabey | Supervision
HECO | Commissioning Support.
Zavtech | Commissioning Support.
Sunbelt | Monitor Controls & Cell Watch During Commissioning.
McKinstry | Complete Installation Of Controls
KBA | Commission UPS #2 & Battery Cabs.
Praetorian | No Activity.
SAFETY / NEAR MISSES:
Tool Box Talk - LOTO
UPCOMING WORK:
Shut Down #3 (Generator Run/ 10hrs), Change Breakers & Final Electrical Connections Scheduled For 11/4.
Prepared By: Matthew J. Meile

## Sheet1
WORK PERFORMED: