## Page 1
Weekly Job Status Report
|  |  | Week Ending: |  | 2025-10-25
PROJECT NAME: | SDC-SEA-SDC42 Chiller:
PROJECT NUMBER: | 25-7-095
ARCHITECT: | Sabey Architecture:
SABEY PROJECT STAFF: | Glenn Parry, Matt Meile
START DATE: | 2025-09-16 | BUDGET: |  |  | 1403699
SCHEDULED COMPLETION: | 2025-11-21 | APPROVED CHANGE ORDERS:
PROJECT % COMPLETE: | 76% | REVISED BUDGET |  |  | 1403699
TENANT: | N/A | EST. COST AT COMPLETION: |  |  | 1403699
|  | CURRENT PROJECTED (+/-) |  |  | 0
SCHEDULE STATUS: | ON SCHEDULE -
TEAM:
| Company | Craft |  | Trade Workers
| Sabey | GC |  | 2
| HECO | Electrical |  | 2
| McKinstry | Mechanical |  | 4
| Sunbelt | Controls |  | 0
| KBA | Commissioning |  | 0
| Shield Of Armor | Safety |  | 0
WORK PERFORMED:
Sabey | Supervision
HECO | Make Final Electrical Connections @ Chiller & Chiller Pump. Install Exterior Lighting.
McKinstry | Insulate Chilled Water Piping. Rough-In Pathway For Controls.
Sunbelt | No Activity.
KBA | No Activity.
Shield Of Armor | No Activity.
SAFETY / NEAR MISSES:
Tool Box Talk - PPE
UPCOMING WORK:
Final Electrical Connections To Chiller, Install Controls. Insulate Chilled Water Piping. Drain/ Flush/ Clean CW Piping.
Prepared By: Matthew J. Meile

## Sheet1
WORK PERFORMED: