## Page 1
Weekly Job Status Report
|  |  | Week Ending: |  | 2025-10-25
PROJECT NAME: | SEA - Providence Pharmacy HVAC Ti
PROJECT NUMBER: | 24-1-061
ARCHITECT: | TGB
SABEY PROJECT STAFF | Rob Pritchett / Sergio Ortega
START DATE: | 2025-03-10 | BUDGET: |  |  | 3584022
SCHEDULED COMPLETION: | 2026-01-23 | APPROVED CHANGE ORDERS:
PROJECT % COMPLETE: | 65% | REVISED BUDGET |  |  | 3584022
TENANT | PROVIDENCE | EST. COST AT COMPLETION: |  |  | 2914398
|  | CURRENT PROJECTED (+/-) |  |  | 669624
SCHEDULE STATUS: | ON SCHEDULE -
TEAM
| Company | Craft |  | Trade Workers
| Sabey | GC |  | 1
| MacDonald Miller | Mechanical |  | 3
| C&P Paint | Paint |  | 0
| Evergreen power | Electrical |  | 0
| Expert Drywall | Framing / GWB |  | 3
| Snyder Roofing | Roofing |  | 3
| DPL | D/F/H Union Labor |  | 0
| Sunbelt Controls | Controls |  | 0
| Brand-Safeway | Scaffolding |  | 2
| Barnhart | Crane |  | 0
| Suppression Systems | Fire alarm |  | 0
| G&W Flooring | Flooring |  | 4
WORK PERFORMED:
Sabey | Supervision
MacDonald Miller | Continue installing new duct work
C&P Paint
Evergreen Power
Expert Drywall | Structural framing on roof for new curbs for RTU's
Snyder Roofing | Finish roofing new curb's
DPL
Sunbelt Controls
Brand-Safeway | Build scaffolding
Barnhart
Suppression Systems
G&W Flooring | Apply moister mitigation and self leveling
SAFETY / NEAR MISSES:
Weekly safety inspection and meeting performed by Rob Pritchett
UPCOMING WORK:
Demo and roof new duct stand locations, apply Install new duct work. Drywall, taping and painting.
Prepared By: Rob Pritchett